## Sheet1
Sub Task Number | Summary | Detailed Description | Days | Start Date | End Date
T1 | Automated Schema Comparison - Read Replica | This task involves automate schema validations for any missing columns across on-prem oracle, postgresql, s3, and ods.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Automate schema validations for any missing columns across On-Prem Oracle, PostgreSQL, S3, and ODS. Validation results reviewed and approved. | 1 | 2025-03-04 | 2025-03-04
T2 | Automated Schema Comparison - CDA | This task involves automate schema validations specifically between oracle and cda.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Automate schema validations specifically between Oracle and CDA. Validation results reviewed and approved. | 1 | 2025-03-04 | 2025-03-04
T3 | Missing Columns Analysis - Oracle Vs Read Replica | This task involves scripts to detect and log mismatched data types between oracle and read replica.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Scripts to detect and log mismatched data types between Oracle and Read Replica. Validation results reviewed and approved. | 3 | 2025-04-22 | 2025-04-22
T4 | Missing Columns Analysis - Oracle Vs CDA | This task involves scripts to detect and log mismatched data types between oracle and cda.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Scripts to detect and log mismatched data types between Oracle and CDA. Validation results reviewed and approved. | 3 | 2025-04-22 | 2025-04-22
T5 | Smoke Test - Extract Data from Oracle to Staging | This task involves schedule daily extraction of oracle data to staging layer.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Schedule daily extraction of Oracle data to staging layer. Validation results reviewed and approved. | 1 | 2025-04-22 | 2025-04-22
T6 | Smoke Test - Extract Data from PostgreSQL to Staging | This task involves schedule daily extraction of postgresql data to staging layer.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Schedule daily extraction of PostgreSQL data to staging layer. Validation results reviewed and approved. | 1 | 2025-04-22 | 2025-04-22
T7 | Smoke Test - Extract Data from S3 to Staging | This task involves automate loads from s3 raw to staging tables.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Automate loads from S3 raw to staging tables. Validation results reviewed and approved. | 1 | 2025-04-22 | 2025-04-22
T8 | Smoke Test - Extract Data from ODS Views | This task involves automate loads from ods views to staging tables.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Automate loads from ODS Views to staging tables. Validation results reviewed and approved. | 1 | 2025-04-22 | 2025-04-22
T9 | Smoke Test - Extract Data from ODS Views (2) | This task involves automate loads from ods views to staging tables.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Automate loads from ODS Views to staging tables. Validation results reviewed and approved. | 1 | 2025-04-22 | 2025-04-22
T10 | Execute Regression Pack against Read Replica Load | This task involves ensure automated testing of data from s3 staging to ods validating data integrity and transformations.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Ensure automated testing of data from S3 staging to ODS validating data integrity and transformations. Validation results reviewed and approved. | 19 | 2025-04-22 | 2025-05-16
T11 | Execute Risk-Based Automated Tests | This task involves automate defect logging, debugging, fixing test failures based on risk prioritization.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Automate defect logging, debugging, fixing test failures based on risk prioritization. Validation results reviewed and approved. | 5 | 2025-05-15 | 2025-05-21
T12 | Cycle 2 Fix Validation and Re-Testing | This task involves automate defect revalidation and retesting cycle 2.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Automate defect revalidation and retesting cycle 2. Validation results reviewed and approved. | 5 | 2025-05-22 | 2025-05-28
T13 | Cycle 3 Fix Validation and Re-Testing | This task involves automate defect revalidation and retesting cycle 3.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Automate defect revalidation and retesting cycle 3. Validation results reviewed and approved. | 5 | 2025-05-29 | 2025-06-04
T14 | Improvement Loop | This task involves log bottlenecks discovered during validation cycles and tag as optimization tasks.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Log bottlenecks discovered during validation cycles and tag as optimization tasks. Validation results reviewed and approved. | 7 | 2025-06-10 | 2025-06-18
T15 | SIT Sign-off & Review | This task involves final validation and stakeholder review/sign-off.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Final validation and stakeholder review/sign-off. Validation results reviewed and approved. | 7 | 2025-06-10 | 2025-06-18
T16 | Execute Regression Pack against S3 - CDA Loaded Data | This task involves automated testing of data integrity for cda loaded datasets.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Automated testing of data integrity for CDA loaded datasets. Validation results reviewed and approved. | 19 | 2025-05-27 | 2025-06-20
T17 | Execute Risk-Based Automated Tests - CDA | This task involves automate defect logging and debugging on cda data based on risk.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Automate defect logging and debugging on CDA data based on risk. Validation results reviewed and approved. | 5 | 2025-06-20 | 2025-06-26
T18 | Cycle 2 Fix Validation and Re-Testing - CDA | This task involves automate defect revalidation and retesting for cda data cycle 2.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Automate defect revalidation and retesting for CDA data cycle 2. Validation results reviewed and approved. | 5 | 2025-06-27 | 2025-07-03
T19 | Cycle 3 Fix Validation and Re-Testing - CDA | This task involves automate defect revalidation and retesting for cda data cycle 3.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Automate defect revalidation and retesting for CDA data cycle 3. Validation results reviewed and approved. | 5 | 2025-07-04 | 2025-07-10
T20 | Improvement Loop - CDA | This task involves log bottlenecks discovered during validation cycles for cda and optimize.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Log bottlenecks discovered during validation cycles for CDA and optimize. Validation results reviewed and approved. | 5 | 2025-07-15 | 2025-07-21
T21 | SIT Sign-off & Review - CDA | This task involves final validation and stakeholder review/sign-off for cda data.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Final validation and stakeholder review/sign-off for CDA data. Validation results reviewed and approved. | 5 | 2025-07-15 | 2025-07-21
T22 | Compare ADF vs Databricks Load Time - Read Replica | This task involves validate high-level ingestion metrics and compare load times between adf and databricks.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Validate high-level ingestion metrics and compare load times between ADF and Databricks. Validation results reviewed and approved. | 4 | 2025-06-02 | 2025-06-05
T23 | Compare ADF vs Databricks Load Time - CDA | This task involves validate high-level ingestion metrics for cda comparing adf and databricks.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Validate high-level ingestion metrics for CDA comparing ADF and Databricks. Validation results reviewed and approved. | 4 | 2025-06-10 | 2025-06-13
T24 | Release Readiness - Read Replica | This task involves release readiness validation activities for read replica workloads.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Release readiness validation activities for Read Replica workloads. Validation results reviewed and approved. | 3 | 2025-06-18 | 2025-06-20
T25 | Release Readiness - CDA | This task involves release readiness validation activities for cda workloads.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Release readiness validation activities for CDA workloads. Validation results reviewed and approved. | 3 | 2025-07-22 | 2025-07-24