# Guidewire CDA Migration – Detailed Task Register with Description & Definition of Done

## GW CDA 33.4 – Discovery, Environment Readiness & Impact Assessment

| Seq | Task | Team | Task Description & Definition of Done |
| --- | --- | --- | --- |
| 1 | CDA Code Familiarisation | QA + Development | Development team to provide CDA walkthrough covering ingestion flow, processing components, deployment approach and downstream dependencies. QA to review available documentation and understand key CDA concepts. DoD: CDA architecture overview completed and QA understanding established. |
| 2 | Review CDA Architecture (Manifest, Watermark, Clone, SCD, ODS Views) | QA | Review CDA processing flow and identify reconciliation checkpoints between Read Replica and CDA. Understand manifest generation, checkpoint processing, watermark handling, Clone tables, SCD processing and ODS View creation. DoD: Architecture understanding documented and reconciliation validation points identified. |
| 3 | Validate Environment Access (Databricks, Catalogues, Jump Server, Permissions) | QA + Data Engineering | Data Engineering to provide required environment access. QA to validate access to Databricks catalogues, lineage tables, Jump Server, source schemas and required testing tools. DoD: All required accesses verified or access gaps formally raised. |
| 4 | CDA Environment Setup | Data Engineering | Configure CDA processing environment and supporting infrastructure required for testing activities. DoD: Environment ready for CDA processing and QA testing. |
| 5 | CDA Code Changes for STD001 | Development | Implement and validate CDA processing changes required to support STD001 source environment. DoD: Code changes completed and successfully deployed. |
| 6 | CDA Deploy into Systest | Development | Deploy CDA processing components into Systest environment and perform deployment validation. DoD: CDA workflows available and operational within Systest. |
| 7 | CDA Views Deploy into Systest | Development | Deploy CDA ODS Views and supporting objects required for reconciliation activities. DoD: ODS Views successfully deployed and accessible. |
| 8 | CDA Log Review and Manifest Validation | Development | Validate workflow execution logs, manifest generation and file processing behaviour. DoD: Manifest processing verified with no critical workflow failures. |
| 9 | Refresh CDA Data in core_tst | Data Engineering | Execute CDA ingestion process and populate CDA datasets into core_tst catalogue. DoD: CDA data available for reconciliation testing. |
| 10 | Refresh Read Replica Data in core_tst | Data Engineering | Refresh Read Replica benchmark datasets into core_tst catalogue for comparison activities. DoD: Read Replica benchmark dataset available and validated. |
| 11 | Validate STD001 Read Replica Data Availability | QA | Assess source data availability directly from STD001 through Jump Server access. Review data volume, active tables, historical data coverage and candidate reconciliation datasets. DoD: Data availability assessment completed and coverage report produced. |
| 12 | Validate CDA Manifest and Source File Availability | QA + Data Engineering | Data Engineering to provide manifest and source file visibility. QA to verify files are generated from STD001, available for processing and successfully loaded into CDA workflows. DoD: Manifest availability, source file generation and ingestion readiness confirmed. |
| 13 | Assess Test Data Coverage Across 691 Guidewire Tables | QA | Analyse data availability across identified Guidewire tables. Assess record counts, CreateTime availability, incremental change activity and reconciliation suitability. DoD: Test data coverage assessment completed with proposed reconciliation scope. |
| 14 | Identify Tables with Large Text/BLOB Columns (>1 MB) | QA | Identify tables containing large object columns and define validation scenarios covering data completeness, truncation risks, special characters and migration behaviour. DoD: Large column inventory completed and validation approach documented. |
| 15 | Build Read Replica vs CDA Table Mapping | Data Engineering | Provide source-to-target mapping between Read Replica ODS Views, CDA ODS Views and downstream processing objects. DoD: Mapping document completed and shared with QA. |
| 16 | Define Watermark Validation Strategy | QA + Data Engineering | Data Engineering to explain watermark implementation and processing timelines. QA to define reconciliation approach ensuring comparisons occur at equivalent business processing points and avoid false mismatches. DoD: Watermark reconciliation strategy documented and agreed. |
| 17 | Downstream Impact Analysis | Data Engineering + Glen | Identify downstream jobs, pipelines, insert views, Silver tables, curated datasets and consumers impacted by CDA switch-over. DoD: Downstream impact assessment completed and reviewed. |
| 18 | Identify Jobs, Pipelines, Views and Curated Tables Consuming ODS Views | Data Engineering | Provide lineage between ODS Views, insert views, downstream jobs, pipelines and curated layers. DoD: End-to-end lineage inventory available for switch-over planning. |
| 19 | Identify Teams Consuming Guidewire Data in core_tst | Data Engineering + PM | Identify stakeholders and teams utilising Guidewire data within core_tst environment. DoD: Consumer inventory completed and communication list established. |
| 20 | Define Business Critical Tables for Production Monitoring | Graham + Glen | Identify business-critical datasets requiring detailed reconciliation and production monitoring coverage. DoD: Business-critical table list agreed and approved. |
| 21 | Establish Test Evidence Repository & Reporting Structure | QA | Create central repository structure for reconciliation outputs, lineage reports, screenshots, defect evidence, sign-off artefacts and execution reporting. DoD: Repository structure established and shared with project team. |
| 22 | Define Reconciliation Entry & Exit Criteria | QA | Define readiness conditions, reconciliation thresholds, acceptable variance limits, defect severity rules and sign-off requirements. DoD: Entry/exit criteria reviewed and approved by stakeholders. |

## GW CDA 33.5 – Reconciliation Automation Development

| Seq | Task | Team | Task Description & Definition of Done |
| --- | --- | --- | --- |
| 23 | Reconciliation Framework Design | QA | Design automated framework covering schema, count, DDL, data format and row-level reconciliation. Align framework with table mappings, watermark strategy and business scope. DoD: Framework design reviewed and approved. |
| 24 | Develop Schema Comparison Automation | QA | Build automation to compare CDA and Read Replica schemas and identify structural differences. DoD: Schema comparison results generated successfully. |
| 25 | Develop Count Comparison Automation | QA | Develop automated count validation using agreed watermark logic and comparison thresholds. DoD: Count validation executed successfully. |
| 26 | Develop DDL Comparison Automation | QA | Build capability to compare table and view definitions across environments. DoD: DDL comparison report generated. |
| 27 | Develop Data Format Validation Automation | QA | Validate datatype consistency, precision, nullability and formatting differences between CDA and Read Replica. DoD: Data format validation report available. |
| 28 | Develop Row-Level Reconciliation Automation | QA | Build row-level comparison framework using business keys and agreed watermark logic. DoD: Row-level reconciliation successfully executed on pilot datasets. |
| 29 | Develop Reconciliation Exception Reporting | QA | Develop reporting capability to capture mismatches and reconciliation failures. DoD: Automated exception reports generated. |
| 30 | Develop QA Reconciliation Dashboard / Execution Reporting | QA | Create execution dashboard showing reconciliation status, mismatches and trends. DoD: Dashboard available for execution reporting. |
| 31 | Automation Framework Integration | QA | Integrate all automation modules into a single execution workflow and scheduling process. DoD: End-to-end framework executes successfully. |
| 32 | Execute Initial Reconciliation Cycle | QA | Execute reconciliation against CDA and Read Replica datasets using agreed scope and watermark strategy. DoD: Reconciliation execution completed and results documented. |
| 33 | Reconciliation Defect Analysis & Triage | QA + Development | Analyse reconciliation failures and identify root causes with Development support. DoD: Defects classified, assigned and tracked. |
| 34 | Defect Review Workshop | QA + Data Engineering + Development | Review reconciliation findings, prioritise issues and agree remediation actions. DoD: Workshop completed and actions assigned. |
| 35 | Production Reconciliation Monitoring Design | Development | Design production reconciliation monitoring pipeline and reporting approach. DoD: Monitoring design approved by stakeholders. |

## GW CDA 33.6 – Validation & Switch-over Preparation

| Seq | Task | Team | Task Description & Definition of Done |
| --- | --- | --- | --- |
| 36 | Schema Drift Validation Approach | QA + Data Engineering | Define validation approach for source-level DDL changes and schema drift behaviour leveraging planned Guidewire changes where available. DoD: Schema drift strategy documented and agreed. |
| 37 | Review LV Motors Change Opportunities for Schema Drift Testing | PM + Data Engineering + Guidewire Team | Assess whether planned LV Motors changes can be utilised to validate schema drift controls. DoD: Decision recorded and opportunity identified. |
| 38 | Develop Schema Drift Automation | QA | Build automation to detect additions, removals, datatype changes and structural differences. DoD: Schema drift automation executed successfully. |
| 39 | Execute Schema Drift Validation | QA | Execute schema drift validation and assess expected behaviour against generated results. DoD: Validation results documented and reviewed. |
| 40 | Define Switch-over Test Scope | Graham | Define impacted downstream scope and validation requirements for switch-over testing. DoD: Switch-over scope approved. |
| 41 | Prepare Switch-over Test Cases | QA | Develop manual test scenarios covering workflow validation, CDC edge cases, large column handling, rollback, downstream jobs and business-critical tables. DoD: Switch-over test pack reviewed and approved. |
| 42 | Define Production Parallel Run Entry & Exit Criteria | QA + PM | Define readiness criteria, monitoring expectations and success conditions for parallel execution. DoD: Parallel run criteria approved. |
| 43 | Notify Teams Using core_tst Environment | PM | Communicate planned testing activities and environment impact to all affected teams. DoD: Stakeholder communication completed. |
| 44 | Execute Switch-over Testing | QA + Data Engineering | Execute switch-over from Read Replica ODS Views to CDA ODS Views and validate operational behaviour, workflow execution, data quality and downstream processing. DoD: Switch-over executed successfully without critical failures. |
| 45 | Validate Rollback Mechanism | QA + Data Engineering | Execute rollback process and confirm restoration of prior state and processing behaviour. DoD: Rollback successfully validated. |
| 46 | Validate Downstream Jobs, Pipelines and Curated Layer Processing | QA + Data Engineering | Validate ADF pipelines, insert views, Silver tables and curated layers continue processing successfully following switch-over. DoD: No critical downstream failures identified. |
| 47 | Reconciliation Sign-off Assessment | QA | Review reconciliation outcomes against agreed success criteria and assess readiness for next phase. DoD: Reconciliation recommendation issued. |
| 48 | Switch-over Sign-off Assessment | QA | Review switch-over outcomes, defect status and operational behaviour. DoD: Switch-over recommendation issued. |
| 49 | Defect Resolution & Retesting | QA + Development | Retest fixes for reconciliation, schema drift and switch-over defects. DoD: Defects closed or formally accepted. |

## GW CDA 33.7 – Production Monitoring & Readiness

| Seq | Task | Team | Task Description & Definition of Done |
| --- | --- | --- | --- |
| 50 | Production Reconciliation Pipeline Build | Development | Build and deploy production reconciliation monitoring pipeline. DoD: Pipeline successfully deployed and validated. |
| 51 | Dashboard Integration with Service Excellence Framework | Service Excellence + Development | Integrate reconciliation reporting into centralised monitoring dashboard framework. DoD: Dashboard reporting operational. |
| 52 | Production Monitoring Readiness Review | PM + QA + Development | Review readiness of reconciliation monitoring, operational processes and reporting. DoD: Monitoring readiness assessment completed. |
| 53 | Production Cutover Workshop | PM + Operations + Data Engineering | Define production cutover approach, dependencies, sequencing and operational responsibilities. DoD: Cutover approach agreed. |
| 54 | Define Watermark Cutover Strategy | Data Engineering | Define cutoff point and transition strategy to avoid duplicate or missing processing during cutover. DoD: Watermark strategy approved. |
| 55 | Define Production Rollback Runbook | Data Engineering + Operations | Document rollback steps, responsibilities, escalation path and recovery procedures. DoD: Rollback runbook completed and reviewed. |
| 56 | Define Production Cutover Entry & Exit Criteria | QA + PM + Operations | Define production readiness conditions, validation checkpoints, rollback triggers and success criteria. DoD: Cutover criteria approved. |
| 57 | Production Readiness Assessment | PM + QA + Development | Review readiness across reconciliation, schema drift, switch-over, monitoring, support and operational controls. DoD: Production readiness recommendation issued. |
| 58 | Production Readiness Sign-off | Project Team | Final review of migration readiness and approval to proceed with production cutover. DoD: Formal sign-off recorded and approved. |

# Additional QA Manual Validation Activities (Supporting Tasks)

- Validate CDC Insert, Update and Delete processing behaviour.

- Validate multiple updates occurring within a single processing window.

- Validate watermark/checkpoint recovery following workflow restart.

- Validate duplicate event handling.

- Validate large column (>1 MB) processing and data integrity.

- Validate workflow execution timing between Read Replica and CDA.

- Validate Databricks scheduling and dependency behaviour.

- Validate manifest generation and source file processing.

- Validate parallel run operational monitoring.

- Validate business-critical table outcomes during switch-over.

- Validate rollback and recovery procedures.

- Validate production cutover watermark behaviour.