## Sheet1
Task ID | Task Name | Description | Owner | Estimation (Days)
T1.1 | Databricks Workspace Setup | Configure clusters, storage, permissions. | Data Engineer | 2
T1.2 | Automation Testing Framework Initialization | PySpark project setup in Databricks with Delta Live Tables | Automation Engineer | 3
T1.3 | Automation Test Plan Creation | Detailed plan outlining approach, tools, roles, deliverables | QA Lead | 3
T1.4 | Automation Framework POC Script & Demo | Develop initial automation demo for validation scripts, showcase to stakeholders | Automation Engineer | 4
T1.5 | Jira Integration Setup | Databricks API integration for automated test case logging in Jira | Automation Engineer | 2
T2.1 | Test Data Identification | Define representative test datasets covering business scenarios and edge cases | Business Analyst / QA Lead | 3
T2.2 | Extract Data from PostgreSQL to Staging | Schedule daily extraction of PostgreSQL data to staging layer | Data Engineer | 3
T2.3 | Extract Data from S3 to Staging | Automate data loads from S3 raw to staging | Data Engineer | 2
T2.4 | Extract Data from ODS and ODS Views | Automate extraction from ODS/Views to testing tables | Data Engineer | 2
T3.1 | Schema Comparison Scripts | Automate schema validations (On-Prem Oracle ↔ PostgreSQL ↔ S3 ↔ ODS) | Automation Engineer | 5
T3.2 | Missing Columns Detection | Automate checks for any missing columns between sources and targets | Automation Engineer | 2
T3.3 | Data Type Mismatch Checks | Automation scripts to detect and log mismatched data types | Automation Engineer | 2
T4.1 | Record Count Validation | Automation scripts for record count validations across all layers | Automation Engineer | 2
T4.2 | Row-Level Data Comparison Scripts | Scripts comparing exact data row-wise for accuracy | Automation Engineer | 4
T4.3 | Duplicate Data Validation | Automation scripts to detect duplicates | Automation Engineer | 2
T4.4 | NULL Count Difference Validation | Automated detection and reporting of differences in NULL counts | Automation Engineer | 2
T4.5 | String Length Validation | Automate checks for string-length discrepancies | Automation Engineer | 2
T4.6 | Scientific Notation Detection | Automation scripts detecting unexpected scientific notations | Automation Engineer | 2
T4.7 | Decimal Precision Violations | Scripts detecting decimal precision mismatches | Automation Engineer | 2
T5.1 | Define Risk-Based Validation Strategy | Identify critical data points and risk areas in Silver/Gold layers | QA Lead / Business Analyst | 3
T5.2 | Risk-Based Validation Script Development | PySpark automation scripts targeting critical/high-risk fields and business rules | Automation Engineer | 4
T5.3 | Execute Risk-Based Automated Tests | Execution and reporting of critical tests results via Databricks Dashboards | QA Tester | 3
T6.1 | Automation Workflow Orchestration | Setup automated end-to-end workflows via Databricks Delta Live Tables pipelines | Automation Engineer | 4
T6.2 | Performance Check Scripts Development | Scripts validating ingestion pipeline performance and SLA compliance | Automation Engineer | 3
T6.3 | Schedule Performance Checks | Automate scheduled performance checks with alerting and dashboard reporting | Data Engineer | 2
T7.1 | Validation Dashboard Setup | Develop dashboards showing real-time validation results | Data Engineer | 4
T7.2 | Daily Automation Validation Reports | Automate reports with daily validation statuses and anomalies | QA Tester | 3
T8.1 | Test Case Preparation in Jira | Manually document additional required test cases/scenarios in Jira for manual checks | QA Tester | 4
T8.2 | SIT Test Execution & Validation | Execute automated SIT test suites and manual validation cases | QA Tester | 5
T8.3 | Defect Logging and Re-Testing | Automated defect logging, debugging, fixing test failures | Automation Engineer / QA Tester | 4
T8.4 | SIT Sign-off & Review | Final validation & stakeholder review/sign-off | Project Lead | 2

## Sheet2
Task ID | Task Name | Description | Owner | Effort (Days) | Start Date | End Date
1. Test Framework Setup & Planning
T1.1 | Databricks Workspace Setup | Configure clusters, storage, permissions. | Data Engineer | 2 | 2025-03-18 | 2025-03-19
T1.2 | Automation Testing Framework Initialization | PySpark project setup in Databricks with Delta Live Tables | Automation Engineer | 3 | 2025-03-19 | 2025-03-21
T1.3 | Automation Test Plan Creation | Detailed plan outlining approach, tools, roles, deliverables | QA Lead | 3 | 2025-03-19 | 2025-03-21
T1.4 | Automation Framework POC Script & Demo | Develop initial automation demo for validation scripts, showcase to stakeholders | Automation Engineer | 4 | 2025-03-21 | 2025-03-24
T1.5 | Jira Integration Setup | Databricks API integration for automated test case logging in Jira | Automation Engineer | 2 | 2025-03-24 | 2025-03-25
2. Data Extraction and Test Data Identification
T2.1 | Test Data Identification | Define representative test datasets covering business scenarios and edge cases | Business Analyst / QA Lead | 3 | 2025-03-25 | 2025-03-27
T2.2 | Extract Data from PostgreSQL to Staging | Schedule daily extraction of PostgreSQL data to staging layer | Data Engineer | 3 | 2025-03-25 | 2025-03-27
T2.3 | Extract Data from S3 to Staging | Automate data loads from S3 raw to staging | Data Engineer | 2 | 2025-03-27 | 2025-03-28
T2.4 | Extract Data from ODS and ODS Views | Automate extraction from ODS/Views to testing tables | Data Engineer | 2 | 2025-03-28 | 2025-03-29
3. Schema Validation Scripts Development
T3.1 | Schema Comparison Scripts | Automate schema validations (On-Prem Oracle ↔ PostgreSQL ↔ S3 ↔ ODS) | Automation Engineer | 5 | 2025-03-29 | 2025-04-03
T3.2 | Missing Columns Detection | Automate checks for any missing columns between sources and targets | Automation Engineer | 2 | 2025-04-03 | 2025-04-04
T3.3 | Data Type Mismatch Checks | Automation scripts to detect and log mismatched data types | Automation Engineer | 2 | 2025-04-04 | 2025-04-05
4. Detailed Data Quality Validation Scripts Development
T4.1 | Record Count Validation | Automation scripts for record count validations across all layers | Automation Engineer | 2 | 2025-04-05 | 2025-04-06
T4.2 | Row-Level Data Comparison Scripts | Scripts comparing exact data row-wise for accuracy | Automation Engineer | 4 | 2025-04-06 | 2025-04-09
T4.3 | Duplicate Data Validation | Automation scripts to detect duplicates | Automation Engineer | 2 | 2025-04-09 | 2025-04-10
T4.4 | NULL Count Difference Validation | Automated detection and reporting of differences in NULL counts | Automation Engineer | 2 | 2025-04-10 | 2025-04-11
T4.5 | String Length Validation | Automate checks for string-length discrepancies | Automation Engineer | 2 | 2025-04-11 | 2025-04-12
T4.6 | Scientific Notation Detection | Automation scripts detecting unexpected scientific notations | Automation Engineer | 2 | 2025-04-12 | 2025-04-13
T4.7 | Decimal Precision Violations | Scripts detecting decimal precision mismatches | Automation Engineer | 2 | 2025-04-13 | 2025-04-14
5. Risk-Based Validation (Silver & Gold Layers)
T5.1 | Define Risk-Based Validation Strategy | Identify critical data points and risk areas in Silver/Gold layers | QA Lead / Business Analyst | 3 | 2025-04-14 | 2025-04-16
T5.2 | Risk-Based Validation Script Development | PySpark automation scripts targeting critical/high-risk fields and business rules | Automation Engineer | 4 | 2025-04-16 | 2025-04-20
T5.3 | Execute Risk-Based Automated Tests | Execution and reporting of critical tests results via Databricks Dashboards | QA Tester | 3 | 2025-04-20 | 2025-04-23
6. Orchestration & Performance Checks
T6.1 | Automation Workflow Orchestration | Setup automated end-to-end workflows via Databricks Delta Live Tables pipelines | Automation Engineer | 4 | 2025-04-23 | 2025-04-27
T6.2 | Performance Check Scripts Development | Scripts validating ingestion pipeline performance and SLA compliance | Automation Engineer | 3 | 2025-04-27 | 2025-04-30
T6.3 | Schedule Performance Checks | Automate scheduled performance checks with alerting and dashboard reporting | Data Engineer | 2 | 2025-04-30 | 2025-05-01
7. Reporting & Dashboarding
T7.1 | Validation Dashboard Setup | Develop dashboards showing real-time validation results | Data Engineer | 4 | 2025-05-01 | 2025-05-05
T7.2 | Daily Automation Validation Reports | Automate reports with daily validation statuses and anomalies | QA Tester | 3 | 2025-05-05 | 2025-05-08
8. SIT Test Execution & Defect Management
T8.1 | Test Case Preparation in Jira | Manually document additional required test cases/scenarios in Jira for manual checks | QA Tester | 4 | 2025-05-08 | 2025-05-11
T8.2 | SIT Test Execution & Validation | Execute automated SIT test suites and manual validation cases | QA Tester | 5 | 2025-05-11 | 2025-05-16
T8.3 | Defect Logging and Re-Testing | Automated defect logging, debugging, fixing test failures | Automation Engineer / QA Tester | 4 | 2025-05-16 | 2025-05-20
T8.4 | SIT Sign-off & Review | Final validation & stakeholder review/sign-off | Project Lead | 2 | 2025-05-20 | 2025-05-22