# Guidewire CDA Migration – Detailed Delivery Plan & Task Register

## GW CDA 33.4 (03 Jun – 16 Jun)

### Discovery, Environment Readiness & Impact Assessment

| Seq | Task | Team | Effort | Dependency |
| --- | --- | --- | --- | --- |
| 1 | CDA Code Familiarisation | QA + Development | 2d | None |
| 2 | Review CDA Architecture (Manifest, Watermark, Clone, SCD, ODS Views) | QA | 2d | None |
| 3 | Validate Environment Access (Databricks, Catalogues, Jump Server, Permissions) | QA + Data Engineering | 2d | None |
| 4 | CDA Environment Setup | Data Engineering | 3d | None |
| 5 | CDA Code Changes for STD001 | Development | 5d | 4 |
| 6 | CDA Deploy into Systest | Development | 2d | 5 |
| 7 | CDA Views Deploy into Systest | Development | 2d | 6 |
| 8 | CDA Log Review and Manifest Validation | Development | 2d | 6 |
| 9 | Refresh CDA Data in core_tst | Data Engineering | 2d | 7 |
| 10 | Refresh Read Replica Data in core_tst | Data Engineering | 2d | 7 |
| 11 | Validate STD001 Read Replica Data Availability | QA | 2d | 10 |
| 12 | Validate CDA Manifest and Source File Availability | QA + Data Engineering | 2d | 9 |
| 13 | Assess Test Data Coverage Across 691 Guidewire Tables | QA | 3d | 11,12 |
| 14 | Identify Tables with Large Text/BLOB Columns (>1 MB) | QA | 2d | 13 |
| 15 | Build Read Replica vs CDA Table Mapping | Data Engineering | 3d | 9,10 |
| 16 | Define Watermark Validation Strategy | QA + Data Engineering | 2d | 15 |
| 17 | Downstream Impact Analysis | Data Engineering + Glen | 5d | None |
| 18 | Identify Jobs, Pipelines, Views and Curated Tables Consuming ODS Views | Data Engineering | 5d | 17 |
| 19 | Identify Teams Consuming Guidewire Data in core_tst | Data Engineering + PM | 2d | 17 |
| 20 | Define Business Critical Tables for Production Monitoring | Graham + Glen | 2d | 17 |
| 21 | Establish Test Evidence Repository & Reporting Structure | QA | 1d | None |
| 22 | Define Reconciliation Entry & Exit Criteria | QA | 2d | 13 |

## GW CDA 33.5 (17 Jun – 30 Jun)

### Reconciliation Automation Development

| Seq | Task | Team | Effort | Dependency |
| --- | --- | --- | --- | --- |
| 23 | Reconciliation Framework Design | QA | 3d | 13,15,16 |
| 24 | Develop Schema Comparison Automation | QA | 3d | 23 |
| 25 | Develop Count Comparison Automation | QA | 3d | 23 |
| 26 | Develop DDL Comparison Automation | QA | 2d | 23 |
| 27 | Develop Data Format Validation Automation | QA | 2d | 23 |
| 28 | Develop Row-Level Reconciliation Automation | QA | 5d | 23 |
| 29 | Develop Reconciliation Exception Reporting | QA | 2d | 23 |
| 30 | Develop QA Reconciliation Dashboard / Execution Reporting | QA | 2d | 23 |
| 31 | Automation Framework Integration | QA | 3d | 24-30 |
| 32 | Execute Initial Reconciliation Cycle | QA | 3d | 31 |
| 33 | Reconciliation Defect Analysis & Triage | QA + Development | 3d | 32 |
| 34 | Defect Review Workshop | QA + Data Engineering + Development | 1d | 33 |
| 35 | Production Reconciliation Monitoring Design | Development | 3d | Parallel |

## GW CDA 33.6 (01 Jul – 14 Jul)

### Validation & Switch-over Preparation

| Seq | Task | Team | Effort | Dependency |
| --- | --- | --- | --- | --- |
| 36 | Schema Drift Validation Approach | QA + Data Engineering | 2d | 33 |
| 37 | Review LV Motors Change Opportunities for Schema Drift Testing | PM + Data Engineering + Guidewire Team | 2d | Parallel |
| 38 | Develop Schema Drift Automation | QA | 3d | 36 |
| 39 | Execute Schema Drift Validation | QA | 2d | 38 |
| 40 | Define Switch-over Test Scope | Graham | 2d | 18 |
| 41 | Prepare Switch-over Test Cases | QA | 3d | 40 |
| 42 | Define Production Parallel Run Entry & Exit Criteria | QA + PM | 2d | 39 |
| 43 | Notify Teams Using core_tst Environment | PM | 1d | 19 |
| 44 | Execute Switch-over Testing | QA + Data Engineering | 4d | 41,43 |
| 45 | Validate Rollback Mechanism | QA + Data Engineering | 2d | 44 |
| 46 | Validate Downstream Jobs, Pipelines and Curated Layer Processing | QA + Data Engineering | 3d | 44 |
| 47 | Reconciliation Sign-off Assessment | QA | 2d | 39 |
| 48 | Switch-over Sign-off Assessment | QA | 2d | 45,46 |
| 49 | Defect Resolution & Retesting | QA + Development | 3d | 44-46 |

## GW CDA 33.7 (15 Jul – 28 Jul)

### Production Monitoring & Readiness

| Seq | Task | Team | Effort | Dependency |
| --- | --- | --- | --- | --- |
| 50 | Production Reconciliation Pipeline Build | Development | 5d | 35 |
| 51 | Dashboard Integration with Service Excellence Framework | Service Excellence + Development | 3d | 50 |
| 52 | Production Monitoring Readiness Review | PM + QA + Development | 2d | 51 |
| 53 | Production Cutover Workshop | PM + Operations + Data Engineering | 2d | 48 |
| 54 | Define Watermark Cutover Strategy | Data Engineering | 2d | 53 |
| 55 | Define Production Rollback Runbook | Data Engineering + Operations | 2d | 53 |
| 56 | Define Production Cutover Entry & Exit Criteria | QA + PM + Operations | 2d | 53 |
| 57 | Production Readiness Assessment | PM + QA + Development | 2d | 52,54,55 |
| 58 | Production Readiness Sign-off | Project Team | 1d | 57 |

# Key Milestones

| Milestone | Target Sprint |
| --- | --- |
| Environment & Data Readiness Complete | GW CDA 33.4 |
| Downstream Impact Analysis Complete | GW CDA 33.4 |
| Reconciliation Framework Complete | GW CDA 33.5 |
| Initial Reconciliation Execution Complete | GW CDA 33.5 |
| Schema Drift Validation Complete | GW CDA 33.6 |
| Switch-over Testing Complete | GW CDA 33.6 |
| QA Validation Sign-off Complete | GW CDA 33.6 |
| Production Reconciliation Monitoring Complete | GW CDA 33.7 |
| Production Readiness Review Complete | GW CDA 33.7 |
| Production Cutover Planning Complete | GW CDA 33.7 |

# Critical Path

Environment Setup → CDA Deployment → Data Refresh → Test Data Assessment → Reconciliation Framework → Reconciliation Execution → Schema Drift Validation → Switch-over Testing → Rollback Validation → QA Sign-off → Production Monitoring Readiness → Cutover Planning → Production Readiness Sign-off