## Sheet1
Sub Task Number | Summary | Detailed Description | Days | Start Date | End Date
T1 | Databricks Workspace Setup | This task involves configure clusters, storage, permissions.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Configure clusters, storage, permissions. Validation results reviewed and approved. | 3 | 2025-03-03 | 2025-03-05
T2 | Automation Testing Framework Initialization | This task involves set up automation testing framework in databricks with delta live tables.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Set up automation testing framework in Databricks with Delta Live Tables. Validation results reviewed and approved. | 1 | 2025-03-03 | 2025-03-03
T3 | Automation Test Plan Creation | This task involves document testing approach, tools, roles, deliverables.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Document testing approach, tools, roles, deliverables. Validation results reviewed and approved. | 3 | 2025-03-04 | 2025-03-06
T4 | Automation Framework POC Script & Demo - 1 | This task involves present initial poc scripts to test manager.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Present initial POC scripts to Test Manager. Validation results reviewed and approved. | 1 | 2025-03-05 | 2025-03-05
T5 | Automation Framework POC Script & Demo - 2 | This task involves showcase poc to project team.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Showcase POC to Project Team. Validation results reviewed and approved. | 1 | 2025-03-06 | 2025-03-06
T6 | Automation Framework POC Script & Demo - 3 | This task involves final framework demonstration for approval.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Final framework demonstration for approval. Validation results reviewed and approved. | 1 | 2025-03-07 | 2025-03-07
T7 | Live Integration Setup | This task involves automate test case logging in jira.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Automate test case logging in Jira. Validation results reviewed and approved. | 3 | 2025-03-03 | 2025-03-06
T8 | Overall Test Coverage Analysis - Review | This task involves review validation coverage for data migration.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Review validation coverage for data migration. Validation results reviewed and approved. | 3 | 2025-03-13 | 2025-03-17
T9 | Automated Test Coverage Analysis | This task involves automated coverage review for critical layers.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Automated coverage review for critical layers. Validation results reviewed and approved. | 1 | 2025-03-11 | 2025-03-11
T10 | Add Coverage for Silver/Gold Layer | This task involves expand framework for business-critical silver/gold layer.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Expand framework for business-critical Silver/Gold layer. Validation results reviewed and approved. | 2 | 2025-03-13 | 2025-03-14
T11 | Review Test Coverage with Stakeholders | This task involves confirm validation coverage with business team.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Confirm validation coverage with business team. Validation results reviewed and approved. | 5 | 2025-03-17 | 2025-03-21
T12 | Add Coverage for Production Feeds | This task involves incorporate production data validation requirements.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Incorporate production data validation requirements. Validation results reviewed and approved. | 2 | 2025-03-17 | 2025-03-18
T13 | Oracle DB Access | This task involves access setup for oracle database.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Access setup for Oracle Database. Validation results reviewed and approved. | 0.5 | 2025-03-19 | 2025-03-19
T14 | VPN Access to AWS S3 | This task involves access buckets for validation between raw/ods layers.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Access buckets for validation between raw/ODS layers. Validation results reviewed and approved. | 0.5 | 2025-03-19 | 2025-03-19
T15 | Jump Server Access - Oracle | This task involves set up jump server for secure connections.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Set up jump server for secure connections. Validation results reviewed and approved. | 0.5 | 2025-03-19 | 2025-03-19
T16 | Read Replica - PostgreSQL DB Access | This task involves provision read replica db access for validation.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Provision Read Replica DB access for validation. Validation results reviewed and approved. | 0.5 | 2025-03-19 | 2025-03-19
T17 | Guidewire UI Access Setup - Legacy | This task involves legacy system validation access.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Legacy system validation access. Validation results reviewed and approved. | 0.5 | 2025-03-23 | 2025-03-23
T18 | Guidewire UI Access Setup - Cloud | This task involves cloud guidewire ui access.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Cloud Guidewire UI access. Validation results reviewed and approved. | 0.5 | 2025-03-23 | 2025-03-23
T19 | Azure DevOps | This task involves provision storage for validation scripts, pipelines.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Provision storage for validation scripts, pipelines. Validation results reviewed and approved. | 0.5 | 2025-03-25 | 2025-03-25
T20 | Teams and Outlook Email ID Creation | This task involves create ids for environment management.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Create IDs for environment management. Validation results reviewed and approved. | 0.5 | 2025-03-25 | 2025-03-25
T21 | New Test Environments on Data Platform | This task involves dedicated staging layer for validations.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Dedicated staging layer for validations. Validation results reviewed and approved. | 0.5 | 2025-03-26 | 2025-03-26
T22 | Staging Table Access | This task involves access to staging tables.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Access to staging tables. Validation results reviewed and approved. | 0.5 | 2025-03-26 | 2025-03-26
T23 | Write Modular Test Functions | This task involves reusable test functions for schema, counts, etc.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Reusable test functions for schema, counts, etc. Validation results reviewed and approved. | 3 | 2025-04-09 | 2025-04-11
T24 | Schema Comparison Scripts | This task involves scripts to compare database schemas.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Scripts to compare database schemas. Validation results reviewed and approved. | 3 | 2025-04-09 | 2025-04-11
T25 | Record Count Validation | This task involves validate counts across database layers.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Validate counts across database layers. Validation results reviewed and approved. | 3 | 2025-04-09 | 2025-04-11
T26 | Row-Level Data Comparison Scripts | This task involves compare row-level data for accuracy.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Compare row-level data for accuracy. Validation results reviewed and approved. | 3 | 2025-04-09 | 2025-04-11
T27 | Duplicate Validation | This task involves detect duplicate records.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Detect duplicate records. Validation results reviewed and approved. | 3 | 2025-04-09 | 2025-04-11
T28 | NULL Count Difference Validation | This task involves report differences in null counts.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Report differences in NULL counts. Validation results reviewed and approved. | 3 | 2025-04-09 | 2025-04-11
T29 | String Validation | This task involves validate string formats and mismatches.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Validate string formats and mismatches. Validation results reviewed and approved. | 3 | 2025-04-09 | 2025-04-11
T30 | Scientific Notation Detection | This task involves detect and validate scientific notations.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Detect and validate scientific notations. Validation results reviewed and approved. | 3 | 2025-04-09 | 2025-04-11
T31 | Precision Mismatch Validation | This task involves check for decimal precision mismatches.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Check for decimal precision mismatches. Validation results reviewed and approved. | 3 | 2025-04-09 | 2025-04-11
T32 | PK/SK Business Key Check | This task involves validate primary and secondary business keys.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Validate primary and secondary business keys. Validation results reviewed and approved. | 3 | 2025-04-09 | 2025-04-11
T33 | Unexpected Integrity Check | This task involves identify unexpected integrity violations.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Identify unexpected integrity violations. Validation results reviewed and approved. | 3 | 2025-04-09 | 2025-04-11
T34 | File Generation Validation - Outbound Layer | This task involves validate outbound file generation.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Validate outbound file generation. Validation results reviewed and approved. | 3 | 2025-04-09 | 2025-04-11
T35 | Integration of ADF Test Pipelines | This task involves trigger adf pipelines for validation runs.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Trigger ADF pipelines for validation runs. Validation results reviewed and approved. | 3 | 2025-04-09 | 2025-04-11