## Sheet1
Task No | Task Duration (mins) | Start Date/Time | End Date/Time | Activity Description | Activity Comments | Task Dependencies
1 | 15 | Post deployment | Post deployment | Verify all PROD Databricks jobs and pipelines are running successfully | Check job status, no failed runs | Deployment completed
2 | 15 | Post deployment | Post deployment | Validate Event Hub ingestion to Bronze tables | Ensure new events are landing | MQS ingestion enabled
3 | 20 | Post deployment | Post deployment | Validate Silver & Gold tables population | Record counts increasing as expected | Bronze validation
4 | 20 | Post deployment | Post deployment | Verify Data Reconciliation job execution | Confirm job ran and produced expected outputs | Reconciliation deployment
5 | 15 | Post deployment | Post deployment | Validate reconciliation results against source counts | No abnormal mismatches | Reconciliation job success
6 | 15 | Post deployment | Post deployment | Verify Quote Cache Deletion pipeline execution | Confirm scheduled job triggered | Quote cache pipeline
7 | 10 | Post deployment | Post deployment | Validate cache deletion effect for recent quotes | Spot check cache records | Cache deletion job
8 | 20 | Post deployment | Post deployment | Validate CoS ODS, Engineering, Analyst & Pricing views | Check view accessibility and data freshness | CoS release
9 | 15 | Post deployment | Post deployment | Validate Vehicle & Area LRT service data availability | Confirm LRT data loaded and accessible | LRT deployment
10 | 10 | Post deployment | Post deployment | Verify PV group permissions on PROD Databricks objects | Access validation only | Security changes
11 | 15 | Post deployment | Post deployment | Monitor PROD logs for errors/exceptions | No critical errors observed | All components live
12 | 10 | Post deployment | Post deployment | Business smoke testing (sample queries / dashboards) | High-level validation only | Data validation complete
13 | 5 | Post deployment | Post deployment | Confirm no alerts triggered in monitoring tools | System stable | Monitoring enabled
Task No | Task Duration (mins) | Start Date/Time | End Date/Time | Activity Description | Activity Comments | Task Dependencies
1 | 20 | Pre-deployment | Pre-deployment | Review PROD release scope and impacted components | Data Recon, Quote Cache, MQS, CoS, LRT | Release plan finalized
2 | 30 | Pre-deployment | Pre-deployment | Validate smoke test scenarios and scripts readiness | Basic data flow & availability checks | Code freeze
3 | 30 | Pre-deployment | Pre-deployment | Prepare PROD smoke test checklist | Focus on critical paths only | Smoke scenarios defined
4 | 45 | Pre-deployment | Pre-deployment | Validate automation framework readiness for PROD monitoring | Incremental data monitoring framework | Automation stable in lower env
5 | 30 | Pre-deployment | Pre-deployment | Move automation framework configuration to PROD | Monitoring only, no data mutation | Security & access approved
6 | 20 | Pre-deployment | Pre-deployment | Validate PROD access and permissions for testing team | Databricks, storage, logs | Access requests approved
7 | 20 | Pre-deployment | Pre-deployment | Validate test queries / dashboards for PROD smoke testing | Read-only validation | Views available
8 | 15 | Pre-deployment | Pre-deployment | Align on data validation tolerances and known issues | Document expected deviations | BA & Dev alignment
9 | 10 | Pre-deployment | Pre-deployment | Final go/no-go readiness confirmation from testing | Testing sign-off for release | All above completed