## Sheet1
🔍 Smoke Testing Scope – Summary
# | Test Area | Objective | Mode | Scope / Assumptions | Outcome Expected | Notes / Comments
1 | Pre-Benchmark Count and Table Check | Capture table count snapshots before switch for ODS, ODS_VIEWS, Curated EDW/IDW, Publish layers | Semi-Automation | Assumed to include all tables, not just scoped 692+151 | Snapshot baseline captured for post-load validation | Coverage may be trimmed if runtime exceeds window
2 | Pre-Schema Benchmark | Capture schema DDLs to detect schema drift after switch | Semi-Automation | Should include all curated EDW/IDW tables where schema drift can impact logic | Schema diff post-load should show no unintended changes | Can be scoped only to critical downstream tables if time constrained
3 | SCD2 Sample Policy Transaction Capture | Track sample SCD2 data behavior before and after switch | Manual | 2–3 sample policies identified per domain; validated in DR if feasible | No breaks in SCD2 continuity; new transactions build on existing state | Yes, can be trialed in DR for early feedback
4 | Duplicate Check (Scoped 692 + 151) | Ensure no duplicates introduced by post-switch loads | Semi-Automation | Scope refined based on preprod execution time | Clean deduplicated datasets after load | May exclude high-volume tables if runtime too long
5 | Jump Server Table Count Snapshot | Extract source table counts before manual load (via jump server) | Manual | All ODS tables assumed | Snapshot must match or be lower-bound after load | Script creation needed for quick access
6 | Post Data Load Count/Schema Comparison | Validate post-load counts and schema match the pre-switch baseline | Semi-Automation | Valid for all layers in step 1, 2, 5 | Record counts ≥ snapshot; schema match confirmed | Automate for consistent accuracy
7 | Post Load Count Check from Read Replica | Ensure load completed fully; rising counts acceptable | Manual | Snapshot from step 1 used as base; only ODS/ODS-Views | No missing data; only growth accepted | Deviations explained with delta timestamps
8 | Post-SCD2 Sample Transaction Check | Revalidate transaction history continuity for sample policies | Manual | Use same policies from step 3 | Expected continuity in SCD2 keys and attributes | Evaluate FAH/publish layer impact if applicable
9 | Post-Scheduled Delta Load (Sunday) | Validate full automated delta ingestion and monitoring | Full Automation | Validates delta pack for lower → prod promotion | No failures or alerts post-load | Must test delta scenario (record updates, new inserts, deletes if applicable)