## Timeline
Phase | Task | Team | Start | End
Phase 1 - Dec (Risk-Based) | E2E Test Data Preparation (Athena/MQS) | Athena / MQS | 2025-11-17 | 2025-11-24
Phase 1 - Dec (Risk-Based) | MI Ingestion Layer SIT | BICoE MI | 2025-11-24 | 2025-12-08
Phase 1 - Dec (Risk-Based) | Cosmos DB Model File Validation | BICoE MI / Pricing | 2025-12-01 | 2025-12-15
Phase 1 - Dec (Risk-Based) | Quote Cache (ADF) Workflow Validation | BICoE MI / Data Engineering | 2025-12-08 | 2025-12-15
Phase 1 - Dec (Risk-Based) | Quote Reconciliation & Data Excellence Checks | BICoE MI / Pricing Ops | 2025-12-15 | 2025-12-22
Phase 1 - Dec (Risk-Based) | Dec Release Sign-off | E2E Test Manager / All Streams | 2025-12-22 | 2025-12-24
Phase 2 - Jan (MVP) | E2E Test Data Refresh & Preparation | Athena / MQS | 2025-12-24 | 2025-12-31
Phase 2 - Jan (MVP) | EDM Core Risk Integration Validation | BICoE MI | 2025-12-31 | 2026-01-14
Phase 2 - Jan (MVP) | EDM Radar Feature Set Validation | BICoE MI / Reporting | 2026-01-07 | 2026-01-21
Phase 2 - Jan (MVP) | Continuity of Service – Pricing View Validation | BICoE MI / Pricing | 2026-01-14 | 2026-01-28
Phase 2 - Jan (MVP) | Full E2E & UAT Preparation | All Workstreams | 2026-01-28 | 2026-02-04
Phase 2 - Jan (MVP) | UAT Execution & Business Sign-off | Pricing / Underwriting / MI Support | 2026-02-04 | 2026-02-18