# QA Task Status Update (As of 16-Jun-2026)

| Seq | Task | Effort | Planned Start | Planned End | Status | QA Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | CDA Code Familiarisation | 2d | 15-Jun | 16-Jun | Complete | Initial CDA architecture walkthrough completed. Understanding established around Clone, SCD, ODS Views, Manifest and Watermark concepts. |
| 2 | Review CDA Architecture (Manifest, Watermark, Clone, SCD, ODS Views) | 2d | 16-Jun | 17-Jun | In Progress | Currently reviewing ingestion flow and identifying reconciliation points between Read Replica and CDA. Additional understanding required around manifest processing and checkpoint management. |
| 3 | Validate Environment Access (Databricks, Catalogues, Jump Server, Permissions) | 2d | 17-Jun | 18-Jun | Not Started | Validate QA access to Databricks catalogues, lineage tables, jump server access, source visibility and required permissions for reconciliation activities. |
| 11 | Validate STD001 Read Replica Data Availability | 2d | 19-Jun | 22-Jun | Not Started | Assess availability of source data within STD001. Identify tables containing sufficient data volume for reconciliation testing. |
| 12 | Validate CDA Manifest and Source File Availability | 2d | 19-Jun | 22-Jun | Not Started | Requires Development/Data Engineering support to verify manifest generation, source file availability and successful ingestion from STD001 into CDA processing. |
| 13 | Assess Test Data Coverage Across 691 Guidewire Tables | 3d | 23-Jun | 25-Jun | Not Started | Assess table population, volume distribution, CreateTime availability and identify candidate tables for reconciliation coverage. |
| 14 | Identify Tables with Large Text/BLOB Columns (>1 MB) | 2d | 26-Jun | 29-Jun | Not Started | Identify large object columns and define validation approach for truncation, integrity and migration verification. |
| 16 | Define Watermark Validation Strategy | 2d | 26-Jun | 29-Jun | Not Started | Define point-in-time comparison strategy between Read Replica and CDA using watermark/cutoff alignment. |
| 21 | Establish Test Evidence Repository & Reporting Structure | 1d | 17-Jun | 17-Jun | Not Started | Create repository structure for reconciliation reports, screenshots, lineage outputs, validation evidence and sign-off artefacts. |
| 22 | Define Reconciliation Entry & Exit Criteria | 2d | 26-Jun | 29-Jun | Not Started | Define readiness criteria, acceptable thresholds, defect handling process and sign-off requirements. |
| 23 | Reconciliation Framework Design | 3d | 30-Jun | 02-Jul | Not Started | Design automation framework covering schema, count, DDL, format and row-level reconciliation. |
| 24 | Develop Schema Comparison Automation | 3d | 03-Jul | 07-Jul | Not Started | Build automated schema comparison capability between Read Replica and CDA ODS Views. |
| 25 | Develop Count Comparison Automation | 3d | 03-Jul | 07-Jul | Not Started | Develop count comparison framework using agreed watermark strategy. |
| 26 | Develop DDL Comparison Automation | 2d | 03-Jul | 06-Jul | Not Started | Build DDL extraction and structural comparison capability. |
| 27 | Develop Data Format Validation Automation | 2d | 03-Jul | 06-Jul | Not Started | Validate datatype consistency and formatting differences between implementations. |
| 28 | Develop Row-Level Reconciliation Automation | 5d | 03-Jul | 09-Jul | Not Started | Build row-level comparison framework for selected tables based on agreed reconciliation scope. |
| 29 | Develop Reconciliation Exception Reporting | 2d | 08-Jul | 09-Jul | Not Started | Produce mismatch reports and reconciliation exception outputs. |
| 30 | Develop QA Reconciliation Dashboard / Execution Reporting | 2d | 08-Jul | 09-Jul | Not Started | Build QA execution dashboard for reconciliation visibility and defect tracking. |
| 31 | Automation Framework Integration | 3d | 10-Jul | 14-Jul | Not Started | Integrate reconciliation modules into a single execution workflow. |
| 32 | Execute Initial Reconciliation Cycle | 3d | 15-Jul | 17-Jul | Not Started | Execute first end-to-end reconciliation across selected Guidewire domains. |
| 33 | Reconciliation Defect Analysis & Triage | 3d | 20-Jul | 22-Jul | Not Started | Investigate schema, count and data mismatches identified during reconciliation execution. |
| 34 | Defect Review Workshop | 1d | 23-Jul | 23-Jul | Not Started | Review reconciliation findings with Development and Data Engineering teams. |
| 36 | Schema Drift Validation Approach | 2d | 24-Jul | 27-Jul | Not Started | Define validation approach leveraging planned Guidewire changes where available. |
| 38 | Develop Schema Drift Automation | 3d | 28-Jul | 30-Jul | Not Started | Build automated schema drift detection framework. |
| 39 | Execute Schema Drift Validation | 2d | 31-Jul | 03-Aug | Not Started | Validate schema change detection and reporting capability. |
| 41 | Prepare Switch-over Test Cases | 3d | 04-Aug | 06-Aug | Not Started | Develop manual validation scenarios for downstream jobs, pipelines, rollback and business-critical tables. |
| 42 | Define Production Parallel Run Entry & Exit Criteria | 2d | 04-Aug | 05-Aug | Not Started | Define readiness criteria for parallel monitoring and production validation activities. |
| 44 | Execute Switch-over Testing | 4d | 07-Aug | 12-Aug | Not Started | Validate downstream jobs and pipeline execution using CDA ODS Views as source. |
| 45 | Validate Rollback Mechanism | 2d | 13-Aug | 14-Aug | Not Started | Validate recovery procedure and rollback capability. |
| 46 | Validate Downstream Jobs, Pipelines and Curated Layer Processing | 3d | 13-Aug | 17-Aug | Not Started | Validate Silver layer loads, impacted jobs and curated processing following switch-over. |
| 47 | Reconciliation Sign-off Assessment | 2d | 18-Aug | 19-Aug | Not Started | Assess reconciliation results against agreed success criteria. |
| 48 | Switch-over Sign-off Assessment | 2d | 20-Aug | 21-Aug | Not Started | Provide QA recommendation on switch-over readiness. |
| 49 | Defect Resolution & Retesting | 3d | 24-Aug | 26-Aug | Not Started | Retest identified issues and confirm resolution. |
| 52 | Production Monitoring Readiness Review | 2d | 27-Aug | 28-Aug | Not Started | Review operational readiness of production reconciliation monitoring. |
| 56 | Define Production Cutover Entry & Exit Criteria | 2d | 31-Aug | 01-Sep | Not Started | Define QA readiness criteria for production cutover. |
| 57 | Production Readiness Assessment | 2d | 02-Sep | 03-Sep | Not Started | Final QA readiness assessment before production cutover planning. |

## Additional QA Activity Identified During Discovery

Validate CDA Workflow Execution and Operational Monitoring

Current Status: Identified during architecture review.

Scope:

- Validate Databricks job scheduling.

- Monitor CDA workflow execution.

- Compare Read Replica vs CDA processing duration.

- Validate manifest generation and processing.

- Validate watermark/checkpoint progression.

- Validate Clone → SCD → ODS View processing completion.

- Review failed runs, retries and recovery behaviour.

- Assess operational stability during parallel monitoring.

Proposed Effort: 3–5 days during reconciliation execution phase.