# QA Workstream Status Update (As of 16-Jun-2026)

| Seq | Task | Effort | Start Date | End Date | Status | QA Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | CDA Code Familiarisation | 2d | 15-Jun-26 | 16-Jun-26 | Completed | Initial review completed. Basic understanding established for CDA ingestion flow, clone tables, SCD processing, ODS Views, manifest and watermark concepts. |
| 2 | Review CDA Architecture (Manifest, Watermark, Clone, SCD, ODS Views) | 2d | 17-Jun-26 | 18-Jun-26 | In Progress | Deep dive discussions ongoing with Data Engineering team. Need confirmation of manifest generation, checkpoint storage and watermark processing behaviour. |
| 3 | Validate Environment Access (Databricks, Catalogues, Jump Server, Permissions) | 2d | 17-Jun-26 | 18-Jun-26 | Not Started | Access validation required for core_tst catalogues, lineage views, jump server access and supporting environments. |
| 11 | Validate STD001 Read Replica Data Availability | 2d | 19-Jun-26 | 22-Jun-26 | Not Started | Validate source data availability and assess daily refresh behaviour directly through STD001 Read Replica environment. |
| 12 | Validate CDA Manifest and Source File Availability | 2d | 19-Jun-26 | 22-Jun-26 | Blocked | Requires Data Engineering support as QA does not currently have access to CDA S3 landing area. |
| 13 | Assess Test Data Coverage Across 691 Guidewire Tables | 3d | 23-Jun-26 | 25-Jun-26 | Not Started | Determine data availability and volume coverage for BC, CC and PC domains. Identify tables suitable for reconciliation validation. |
| 14 | Identify Tables with Large Text/BLOB Columns (>1 MB) | 2d | 26-Jun-26 | 29-Jun-26 | Not Started | Identify candidate tables requiring large object validation and assess data availability. |
| 16 | Define Watermark Validation Strategy | 2d | 30-Jun-26 | 01-Jul-26 | Not Started | Define point-in-time reconciliation approach, watermark alignment strategy and handling of tables without CreateTime columns. |
| 21 | Establish Test Evidence Repository & Reporting Structure | 1d | 17-Jun-26 | 17-Jun-26 | Not Started | Create repository structure for reconciliation results, schema drift evidence, switch-over evidence and defect tracking. |
| 22 | Define Reconciliation Entry & Exit Criteria | 2d | 26-Jun-26 | 29-Jun-26 | Not Started | Define acceptance criteria, reconciliation thresholds, defect classification and sign-off requirements. |
| 23 | Reconciliation Framework Design | 3d | 30-Jun-26 | 02-Jul-26 | Not Started | Design automation framework covering schema, count, DDL, format and row-level comparison. |
| 24 | Develop Schema Comparison Automation | 3d | 03-Jul-26 | 07-Jul-26 | Not Started | Compare CDA ODS Views against Read Replica benchmark structures. |
| 25 | Develop Count Comparison Automation | 3d | 03-Jul-26 | 07-Jul-26 | Not Started | Table-level and watermark-based count validation. |
| 26 | Develop DDL Comparison Automation | 2d | 03-Jul-26 | 06-Jul-26 | Not Started | Detect structural differences between Read Replica and CDA implementations. |
| 27 | Develop Data Format Validation Automation | 2d | 06-Jul-26 | 07-Jul-26 | Not Started | Validate datatype consistency and formatting behaviour. |
| 28 | Develop Row-Level Reconciliation Automation | 5d | 03-Jul-26 | 09-Jul-26 | Not Started | Primary automation component for row-level comparison between CDA and Read Replica ODS Views. |
| 29 | Develop Reconciliation Exception Reporting | 2d | 08-Jul-26 | 09-Jul-26 | Not Started | Generate mismatch reporting and exception outputs. |
| 30 | Develop QA Reconciliation Dashboard / Execution Reporting | 2d | 08-Jul-26 | 09-Jul-26 | Not Started | Lightweight QA execution dashboard for validation activities. |
| 31 | Automation Framework Integration | 3d | 10-Jul-26 | 14-Jul-26 | Not Started | Integrate all automation components and prepare execution workflow. |
| 32 | Execute Initial Reconciliation Cycle | 3d | 15-Jul-26 | 17-Jul-26 | Not Started | First full reconciliation execution against identified table scope. |
| 33 | Reconciliation Defect Analysis & Triage | 3d | 20-Jul-26 | 22-Jul-26 | Not Started | Analyse discrepancies and work with Data Engineering team on root cause investigation. |
| 36 | Schema Drift Validation Approach | 2d | 20-Jul-26 | 21-Jul-26 | Not Started | Finalise schema drift validation approach based on available Guidewire change opportunities. |
| 38 | Develop Schema Drift Automation | 3d | 22-Jul-26 | 24-Jul-26 | Not Started | Automate detection of column additions, removals, datatype changes and nullability changes. |
| 39 | Execute Schema Drift Validation | 2d | 27-Jul-26 | 28-Jul-26 | Not Started | Execute schema drift validation against agreed test scenarios. |
| 41 | Prepare Switch-over Test Cases | 3d | 27-Jul-26 | 29-Jul-26 | Not Started | Prepare downstream validation and operational test scenarios. |
| 42 | Define Production Parallel Run Entry & Exit Criteria | 2d | 29-Jul-26 | 30-Jul-26 | Not Started | Define conditions required to enter and exit parallel monitoring phase. |
| 44 | Execute Switch-over Testing | 4d | 31-Jul-26 | 05-Aug-26 | Not Started | Validate downstream jobs, pipelines and curated layer processing using CDA source. |
| 45 | Validate Rollback Mechanism | 2d | 06-Aug-26 | 07-Aug-26 | Not Started | Validate rollback process and recovery procedures. |
| 46 | Validate Downstream Jobs, Pipelines and Curated Layer Processing | 3d | 06-Aug-26 | 10-Aug-26 | Not Started | Confirm no functional regression after source transition. |
| 47 | Reconciliation Sign-off Assessment | 2d | 11-Aug-26 | 12-Aug-26 | Not Started | Assess reconciliation outcomes and readiness for switch-over recommendation. |
| 48 | Switch-over Sign-off Assessment | 2d | 13-Aug-26 | 14-Aug-26 | Not Started | Final QA assessment and recommendation. |
| 52 | Production Monitoring Readiness Review | 2d | TBD | TBD | Future Phase | Dependent on completion of development-owned monitoring solution. |
| 56 | Define Production Cutover Entry & Exit Criteria | 2d | TBD | TBD | Future Phase | To be completed during production readiness planning. |

## Current QA Risks / Blockers

- CDA S3 landing area visibility not available to QA.

- Confirmation required on CDA manifest generation and checkpoint storage locations.

- Awaiting downstream impact analysis and lineage mapping from Data Engineering.

- Business-critical table scope for production monitoring yet to be agreed.

- Schema drift validation dependent on availability of Guidewire source-level DDL changes.