## Sheet1
Sub Task Number | Summary | Detailed Description | Days | Start Date | End Date
T1 | Define Risk-Based Validation Strategy | This task involves identify critical data points and risk areas in silver/gold layer.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Identify critical data points and risk areas in Silver/Gold layer. Validation results reviewed and approved. | 3 | 2025-04-09 | 2025-04-11
T2 | Risk-Based Validation Script Development | This task involves develop pyspark scripts targeting critical/high-risk fields and business rules.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Develop PySpark scripts targeting critical/high-risk fields and business rules. Validation results reviewed and approved. | 18 | 2025-04-14 | 2025-05-02
T3 | Create Controlled Test Data | This task involves develop sample datasets that represent typical data loads, edge cases and boundary conditions.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Develop sample datasets that represent typical data loads, edge cases and boundary conditions. Validation results reviewed and approved. | 15 | 2025-03-04 | 2025-04-17
T4 | Data Reset Mechanism | This task involves define the resetting or cleaning of the bronze tables between test runs to ensure isolation and consistency.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Define the resetting or cleaning of the bronze tables between test runs to ensure isolation and consistency. Validation results reviewed and approved. | 3 | 2025-04-15 | 2025-04-17
T5 | Test Data Scenario Identification Support | This task involves define representative test datasets covering business scenarios and edge cases.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Define representative test datasets covering business scenarios and edge cases. Validation results reviewed and approved. | 3 | 2025-04-15 | 2025-04-17
T6 | Integrate with CI/CD Pipelines | This task involves use azure devops to run tests automatically after changes to the pipeline or data scripts.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Use Azure DevOps to run tests automatically after changes to the pipeline or data scripts. Validation results reviewed and approved. | 5 | 2025-03-24 | 2025-03-28
T7 | Use Databricks Jobs | This task involves use databricks to schedule and execute tests scripts as databricks jobs.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Use Databricks to schedule and execute tests scripts as Databricks Jobs. Validation results reviewed and approved. | 2 | 2025-03-25 | 2025-03-26
T8 | Parameterized Test Runs | This task involves enable test scripts to accept parameters for flexible test execution.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Enable test scripts to accept parameters for flexible test execution. Validation results reviewed and approved. | 5 | 2025-03-26 | 2025-04-01
T9 | Repository Creation in DevOps | This task involves set up github/devops repository to store all automation scripts, configurations, and test artifacts.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Set up GitHub/DevOps repository to store all automation scripts, configurations, and test artifacts. Validation results reviewed and approved. | 8 | 2025-03-24 | 2025-04-02
T10 | Set Up Notifications | This task involves configure notifications for test results.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Configure notifications for test results. Validation results reviewed and approved. | 4 | 2025-04-07 | 2025-04-10
T11 | Integrate with Databricks Monitoring - Daily Automation | This task involves integrate into databricks built-in monitoring tools and azure monitor to track pipeline execution and test status.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Integrate into Databricks built-in monitoring tools and Azure Monitor to track pipeline execution and test status. Validation results reviewed and approved. | 8 | 2025-04-07 | 2025-04-16
T12 | Dashboards for Test Results | This task involves use notebooks to visualize test run metrics and outcomes - develop dashboards showing real-time validation results.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Use Notebooks to visualize test run metrics and outcomes - Develop dashboards showing real-time validation results. Validation results reviewed and approved. | 8 | 2025-04-07 | 2025-04-16
T13 | Feedback Loop | This task involves collect feedback from stakeholders and test results to improve and expand the test cases over time.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Collect feedback from stakeholders and test results to improve and expand the test cases over time. Validation results reviewed and approved. | 3 | 2025-03-31 | 2025-04-02
T14 | Update Tests | This task involves continuously add new test cases as the adf pipeline evolves or new requirements emerge.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Continuously add new test cases as the ADF pipeline evolves or new requirements emerge. Validation results reviewed and approved. | 7 | 2025-04-09 | 2025-04-17
T15 | Monitor for Flakiness | This task involves identify and fix any tests that produce inconsistent results to maintain reliability.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Identify and fix any tests that produce inconsistent results to maintain reliability. Validation results reviewed and approved. | 6 | 2025-04-09 | 2025-04-16
T16 | Develop and Version Control Test Scripts | This task involves develop and maintain version control of test scripts.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Develop and maintain version control of test scripts. Validation results reviewed and approved. | 14 | 2025-03-24 | 2025-04-02
T17 | Trigger Tests | This task involves automatically trigger the regression pack after a pipeline run.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Automatically trigger the regression pack after a pipeline run. Validation results reviewed and approved. | 2 | 2025-03-24 | 2025-03-25
T18 | Run Tests | This task involves validate schema validations, transformations and file generations after pipeline run.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Validate schema validations, transformations and file generations after pipeline run. Validation results reviewed and approved. | 2 | 2025-03-25 | 2025-03-26
T19 | Capture and Log Results | This task involves capture and log results into delta lake for tracking and historical analysis.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Capture and log results into Delta Lake for tracking and historical analysis. Validation results reviewed and approved. | 2 | 2025-03-27 | 2025-03-28
T20 | Alert and Report | This task involves alert the team via email or teams for failures and generate daily/weekly reports.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Alert the team via email or Teams for failures and generate daily/weekly reports. Validation results reviewed and approved. | 2 | 2025-03-31 | 2025-04-01
T21 | Integrate Scripts into CI/CD Pipeline | This task involves continuous validation through ci/cd pipeline integration.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Continuous validation through CI/CD pipeline integration. Validation results reviewed and approved. | 2 | 2025-03-31 | 2025-04-01
T22 | Test Case Preparation in Jira | This task involves document additional required test cases/scenarios in jira.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Document additional required test cases/scenarios in Jira. Validation results reviewed and approved. | 8 | 2025-04-07 | 2025-04-16
T23 | Defect Location and Retesting | This task involves automated defect logging, debugging, fixing test failures.. It ensures the necessary setup or validation is achieved. **Definition of Done (DOD):** Automated defect logging, debugging, fixing test failures. Validation results reviewed and approved. | 8 | 2025-04-07 | 2025-04-16