## LV Motor Testing Jira Plan
Phase | Jira Type | Summary | Fixed Version | Description | Acceptance Criteria | Traceability To | Dependency
Test Management | Task | LV Motor – SIT Test Strategy and Scope | TBC | Define ingestion-layer SIT scope, responsibilities, exclusions, milestones and entry/exit criteria. | SIT plan approved; Silverish/Silver/DEA excluded. | RLIS01–RLIS16 | BICoE / source / DEA scope alignment
Test Management | Task | LV Motor – Test Coverage and Traceability | TBC | Build coverage matrix against requirements and existing Jira delivery tasks. | Every BICoE-owned in-scope item mapped to scenarios and Jira tasks. | RLIS01–RLIS16 | Confirmed requirements
Test Management | Task | LV Motor – Test Coordination with Upstream | TBC | Coordinate source-owned scenarios, test-data creation, expected outputs and issue triage. | Source team commitments, scenarios and contacts recorded. | Cross-cutting | Upstream source readiness
Test Management | Task | LV Motor – SIT Environment Readiness – MQS | TBC | Check MQS feed, Event Hub connectivity, landing and DLT processing routes, permissions and monitoring. | Environment readiness checklist signed off. | RLIS04 | MQS Event Hub configuration
Test Management | Task | LV Motor – SIT Environment Readiness – CRS | TBC | Confirm CRS SSP BI feed/test environment, connectivity, access and agreed test data. | CRS readiness confirmed or tracked as blocker. | RLIS10 | CRS team / feed setup
Test Management | Task | LV Motor – Smoke Test – MQS End-to-End | TBC | Verify upstream can create MQS events and BICoE can receive, land and process samples. | Traceable smoke-test events visible through in-scope ingestion checkpoints. | RLIS04 | MQS ready and source test records
Test Management | Task | LV Motor – Smoke Test – CRS Feed | TBC | Validate CRS feed arrival and basic ingestion checkpoints. | Sample CRS feed verified, or blocker logged. | RLIS10 | CRS source data
Test Management | Task | LV Motor – Cycle 1 Planning and Data Readiness | TBC | Schedule end-to-end Cycle 1, source inputs, evidence, participants and go/no-go. | Cycle 1 scenarios, data and owners confirmed. | Cross-cutting | Passed smoke test
Test Management | Task | LV Motor – Cycle 1 Execution Management | TBC | Track daily progress, results, dependencies and reconciliation of scenario coverage. | Daily status and evidence links captured. | Cross-cutting | Cycle 1 ready
Test Management | Task | LV Motor – Defect Management and Triage | TBC | Raise, prioritise, assign and triage BICoE ingestion defects with source/engineering teams. | Defects reproducible, owned and tracked through retest. | Cross-cutting | Execution results
Test Management | Task | LV Motor – Cycle 2 Planning and Execution (Conditional) | TBC | Execute targeted retest/regression cycle where Cycle 1 defects or changes justify it. | Impacted scenarios rerun and outcomes logged; cycle need documented. | Cross-cutting | Defect fix availability
Test Management | Task | LV Motor – SIT Closure and Sign-Off | TBC | Collate results, deviations, defects, coverage, evidence and exit recommendation. | Scope-specific SIT closure record approved. | Cross-cutting | Completion of agreed tests
Test Design | Task | LV Motor – Five Pricing Data Contract Views (RLIS01) – Test Design | TBC | Design per-view validation for each of the five pricing data-contract views; document expected columns, populated data, applicable freshness and access path. Do not treat views as DLT table count. | Approved test scenarios, expected results and source-to-ingestion traceability documented. | RLIS01 | Confirmed names and contracts for five views; upstream expected results
Test Execution | Task | LV Motor – Five Pricing Data Contract Views (RLIS01) – Test Execution | TBC | Validate five named pricing views against agreed contracts using upstream-produced scenarios and BICoE ingestion outputs. | Evidence captured; expected vs actual results verified; defects logged and retested. | RLIS01 | Confirmed names and contracts for five views; upstream expected results
Test Design | Task | LV Motor – Data Contract View Permissions (RLIS02) – Test Design | TBC | Design allowed/denied permission tests for the five contract views and relevant roles. | Approved test scenarios, expected results and source-to-ingestion traceability documented. | RLIS02 | Defined roles/permissions; environment grants
Test Execution | Task | LV Motor – Data Contract View Permissions (RLIS02) – Test Execution | TBC | Verify each view is accessible to permitted roles and restricted for non-permitted roles. | Evidence captured; expected vs actual results verified; defects logged and retested. | RLIS02 | Defined roles/permissions; environment grants
Test Design | Task | LV Motor – MQS Event Hub to Landing Ingestion – Test Design | TBC | Design per-message ingestion tests for Event Hub receipt, landing persistence, counts, identifiers, schema and exception paths. | Approved test scenarios, expected results and source-to-ingestion traceability documented. | RLIS04 | Event Hub access; agreed payloads and source scenarios
Test Execution | Task | LV Motor – MQS Event Hub to Landing Ingestion – Test Execution | TBC | Trace representative source events to landing, capture message identities and compare source expectations. | Evidence captured; expected vs actual results verified; defects logged and retested. | RLIS04 | Event Hub access; agreed payloads and source scenarios
Test Design | Task | LV Motor – DLT Processing – Full Applicable Table Inventory – Test Design | TBC | Agree exact DLT table inventory with development; define table-level test matrix across ALL applicable LV Motor DLT tables (not capped at seven); cover completeness, processing, watermark and dedup logic as implemented. | Approved test scenarios, expected results and source-to-ingestion traceability documented. | RLIS04 | Developer-approved DLT table inventory, lineage and business logic
Test Execution | Task | LV Motor – DLT Processing – Full Applicable Table Inventory – Test Execution | TBC | Validate records and transformation outcomes through every confirmed in-scope DLT table; test dedup/watermarks/reprocessing only where present. | Evidence captured; expected vs actual results verified; defects logged and retested. | RLIS04 | Developer-approved DLT table inventory, lineage and business logic
Test Design | Task | LV Motor – Raw Enrichment Tables – Test Design | TBC | Identify raw enrichment outputs from quote/cost messages and expected per-table generation cases. | Approved test scenarios, expected results and source-to-ingestion traceability documented. | RLIS05 | Enrichment table inventory; source event fixtures
Test Execution | Task | LV Motor – Raw Enrichment Tables – Test Execution | TBC | Validate enrichment output presence, values and linkage to originating quote/cost messages within ingestion boundary. | Evidence captured; expected vs actual results verified; defects logged and retested. | RLIS05 | Enrichment table inventory; source event fixtures
Test Design | Task | LV Motor – MyLicence DVLA 30-Day Data Retention – Test Design | TBC | Specify lifecycle cases for unconverted quotes crossing 30 days and exceptions for converted quotations. | Approved test scenarios, expected results and source-to-ingestion traceability documented. | RLIS06 | Confirmed retention trigger, job schedule, table inventory and synthetic aged test data
Test Execution | Task | LV Motor – MyLicence DVLA 30-Day Data Retention – Test Execution | TBC | Demonstrate eligible DVLA data is removed after 30 days from agreed BICoE tables and unaffected cases remain as defined. | Evidence captured; expected vs actual results verified; defects logged and retested. | RLIS06 | Confirmed retention trigger, job schedule, table inventory and synthetic aged test data
Test Design | Task | LV Motor – PolicyCenter–MQS Correlation – Test Design | TBC | Agree correlation keys, sequencing and expected outcomes when PolicyCenter records match/do not match MQS events. | Approved test scenarios, expected results and source-to-ingestion traceability documented. | RLIS07 | Engineering/source confirmed correlation rules and test cases
Test Execution | Task | LV Motor – PolicyCenter–MQS Correlation – Test Execution | TBC | Validate ingestion-layer correlation outputs for matched, unmatched and late-arriving records. | Evidence captured; expected vs actual results verified; defects logged and retested. | RLIS07 | Engineering/source confirmed correlation rules and test cases
Test Design | Task | LV Motor – Aggregator Join and Tiering – Test Design | TBC | Define aggregator join expectations, identifiers, tiering rules and data preconditions. | Approved test scenarios, expected results and source-to-ingestion traceability documented. | RLIS08 | Detailed RLIS08 acceptance criteria and input feeds
Test Execution | Task | LV Motor – Aggregator Join and Tiering – Test Execution | TBC | Validate agreed aggregation/join output at ingestion boundary against source-produced sample results. | Evidence captured; expected vs actual results verified; defects logged and retested. | RLIS08 | Detailed RLIS08 acceptance criteria and input feeds
Test Design | Task | LV Motor – CRS SSP BI Feed Ingestion Regression – Test Design | TBC | Define regression coverage for existing CRS SSP BI feed ingestion and any LV Motor impacts. | Approved test scenarios, expected results and source-to-ingestion traceability documented. | RLIS10 | Confirmed changed components and CRS regression baseline
Test Execution | Task | LV Motor – CRS SSP BI Feed Ingestion Regression – Test Execution | TBC | Run agreed CRS feed regression and verify pre-existing ingestion continues unchanged. | Evidence captured; expected vs actual results verified; defects logged and retested. | RLIS10 | Confirmed changed components and CRS regression baseline
Test Design | Task | LV Motor – Reconciliation at Ingestion Boundary – Test Design | TBC | Specify source-versus-landing/DLT checks for counts, missing/duplicates, identifiers and acknowledged processing delay. | Approved test scenarios, expected results and source-to-ingestion traceability documented. | RLIS11 | Source extract or expected IDs; reconciliation definitions
Test Execution | Task | LV Motor – Reconciliation at Ingestion Boundary – Test Execution | TBC | Execute forward/reverse checks where possible using source-supplied record list and capture explainable differences. | Evidence captured; expected vs actual results verified; defects logged and retested. | RLIS11 | Source extract or expected IDs; reconciliation definitions
Test Design | Task | LV Motor – Confused.com Quote Retention / Data Access – Test Design | TBC | Confirm quote retention rule, required access and which ingestion tables/views belong to BICoE. | Approved test scenarios, expected results and source-to-ingestion traceability documented. | RLIS12 | Clarified RLIS12 data ownership and retention criteria
Test Execution | Task | LV Motor – Confused.com Quote Retention / Data Access – Test Execution | TBC | Execute agreed ingestion-level retention/access cases without assuming downstream scope. | Evidence captured; expected vs actual results verified; defects logged and retested. | RLIS12 | Clarified RLIS12 data ownership and retention criteria
Test Design | Task | LV Motor – Quote Cache Deletion – Test Design | TBC | Agree quote cache location, deletion trigger and whether validation is BICoE-owned. | Approved test scenarios, expected results and source-to-ingestion traceability documented. | RLIS13 | Cache service owner; trigger and acceptance criteria
Test Execution | Task | LV Motor – Quote Cache Deletion – Test Execution | TBC | Verify agreed deletion and any observable ingestion-side consequence; evidence scoped to owned components. | Evidence captured; expected vs actual results verified; defects logged and retested. | RLIS13 | Cache service owner; trigger and acceptance criteria
Test Design | Task | LV Motor – Personal Data Access Controls (Provisional) – Test Design | TBC | Clarify whether personal data access tests are BICoE ingestion owned; prepare positive/negative access cases if confirmed. | Approved test scenarios, expected results and source-to-ingestion traceability documented. | RLIS14 | Ownership, roles and privacy requirements TBC
Test Execution | Task | LV Motor – Personal Data Access Controls (Provisional) – Test Execution | TBC | Execute only confirmed BICoE access-control checks and capture approved role outcomes. | Evidence captured; expected vs actual results verified; defects logged and retested. | RLIS14 | Ownership, roles and privacy requirements TBC
Test Design | Task | LV Motor – Ingestion Non-Functional Tests (Provisional) – Test Design | TBC | Confirm throughput, latency, resiliency, replay and monitoring expectations for Event Hub-to-DLT processing. | Approved test scenarios, expected results and source-to-ingestion traceability documented. | RLIS15 | NFR thresholds, load data, test environment and ownership TBC
Test Execution | Task | LV Motor – Ingestion Non-Functional Tests (Provisional) – Test Execution | TBC | Run mutually agreed checks against documented thresholds within ingestion layer. | Evidence captured; expected vs actual results verified; defects logged and retested. | RLIS15 | NFR thresholds, load data, test environment and ownership TBC
Test Design | Task | LV Motor – Vehicle and Area LRT / Cosmos DB (Provisional) – Test Design | TBC | Determine whether Cosmos DB service has BICoE ingestion integration and define only owned validation points. | Approved test scenarios, expected results and source-to-ingestion traceability documented. | RLIS16 | Service integration diagram and BICoE responsibility TBC
Test Execution | Task | LV Motor – Vehicle and Area LRT / Cosmos DB (Provisional) – Test Execution | TBC | Run only agreed tests of BICoE-facing integration; service-specific testing stays with owner. | Evidence captured; expected vs actual results verified; defects logged and retested. | RLIS16 | Service integration diagram and BICoE responsibility TBC
Test Design | Task | LV Motor – End-to-End Ingestion Regression – Test Design | TBC | Define core existing MQS, DLT and view validation paths to rerun after fixes. | Approved test scenarios, expected results and source-to-ingestion traceability documented. | Cross-cutting | Agreed regression baseline
Test Execution | Task | LV Motor – End-to-End Ingestion Regression – Test Execution | TBC | Verify that new changes do not disrupt previously passing ingestion paths. | Evidence captured; expected vs actual results verified; defects logged and retested. | Cross-cutting | Agreed regression baseline

## Scope & Assumptions
Topic | Updated LV Motor testing interpretation
DLT versus views | Five pricing data-contract views (RLIS01/02) are NOT the DLT table set (RLIS04). Keep separate design/execution tasks.
DLT inventory | White-background BICoE diagram indicates more DLT tables than the previously stated seven. Developer to confirm exact in-scope set; do not impose seven-table cap.
Source ownership | Source teams define/create test scenarios and test data; BICoE validates received and ingested outputs.
Ingestion boundary | BICoE tests Event Hub → landing → DLT and contracted views only where owned. Silverish, Silver, Gold, DEA transformations excluded.
Five views | Exact view names and contract versions to be confirmed against RLIS01/RLIS02 and BICoE architecture.
Environment | MQS Event Hub and CRS SSP BI feed readiness and smoke testing precede formal Cycle 1.
Cycles | Cycle 1 required; Cycle 2 conditional on defects/changes; include triage, evidence and closure.
RLIS03 | Mapping work is engineering-owned; no standalone mapping-specific BICoE test task. Validate outputs where relevant to ingestion.
RLIS09 | Feed definition is not the BICoE ingestion test item; RLIS10 retains CRS ingestion regression.
Provisional | RLIS14–16 tests need ownership/acceptance criteria confirmation; retain planning placeholders.
Existing workbook | Recreated from conversation scope because the previously referenced 43-task spreadsheet was not present among accessible files; this edition has 44 independently scoped tasks.