## Combined PM Tracker
Activity | Resource | Dependencies | Row Type | Source / Placement
Data products contract | Nita |  | Existing | Original screenshot row 2
Upstream data mappings (RLPs) | Callum |  | Existing | Original screenshot row 3
BICoE data mapping updates | Callum |  | Existing | Original screenshot row 4
BICoE impact assessment | Gaurav and Test team |  | Existing | Original screenshot row 5
BICoE SIT test planning, scope and test strategy | Test team | Confirm BICoE ingestion boundary and ownership | Added | After original row 5
New non-prod event hubs built and handed over to BICoE | AZ Tech (Cloud Squad) |  | Existing | Original screenshot row 6
Setting up new keys/secrets for new event hub | Gaurav/Cloud Squad |  | Existing | Original screenshot row 7
BICoE connectivity test to new non-prod event hubs | Gaurav |  | Existing | Original screenshot row 8
MQS and CRS test environment readiness assessment | BICoE / Cloud / Source teams (TBC) | Event hubs, secrets, landing/DLT pipelines, CRS feed availability | Added | After original row 8
Pricing ART signed off test data from smoke testing and integration testing | External - Placeholder (uncertain) |  | Existing | Original screenshot row 9
E2E test scenarios and source test data coordination | Test team / Source teams (TBC) | Source teams define/create scenario data; confirm record identifiers and expected outcomes | Added | After original row 9
Start of e2e Testing Phase | External - Placeholder (uncertain) |  | Existing | Original screenshot row 10
New schema for BLD & TST (incl new folder structure) | Gaurav |  | Existing | Original screenshot row 11
Build new databricks pipeline for landing messages |  |  | Existing | Original screenshot row 12
Build DLT pipelines for 7 message types |  |  | Existing | Original screenshot row 13
Build Views for 5 variant types |  |  | Existing | Original screenshot row 14
Five data contract views – test design and access permissions | Test team (TBC) | RLIS01/02; five pricing views; access permissions | Added | After original row 14
Ingest test data, build and test 7 message types (build and internal testing) | Gaurav and Test team |  | Existing | Original screenshot row 15
MQS ingestion / DLT – formal test design | Test team (TBC) | RLIS04; agree applicable DLT tables; no cap imposed on table count | Added | After original row 15
MQS ingestion / DLT – formal test execution | Test team (TBC) | Event Hub → landing → DLT; completeness, watermark and dedup where applicable | Added | After original row 15
Raw enrichment – test design and execution | Test team (TBC) | RLIS05; quote/cost message enrichment in ingestion scope | Added | After original row 15
MyLicence DVLA 30-day retention – test design and execution | Test team (TBC) | RLIS06; remove DVLA data for quotes remaining unconverted beyond 30 days | Added | After original row 15
Test prep and smoke testing |  |  | Existing | Original screenshot row 16
SIT Cycle 1 – end-to-end test execution and coordination | Test team / Source teams (TBC) | Run after environment, smoke and test data readiness | Added | After original row 16
Test Views for 5 variant types |  |  | Existing | Original screenshot row 17
Five data contract views – formal test execution | Test team (TBC) | RLIS01/02; five views and permission outcomes | Added | After original row 17
Correlate PC Quote ID in test | ? |  | Existing | Original screenshot row 18
PolicyCenter / MQS correlation – test design and execution | Test team (TBC) | RLIS07; confirm join/correlation logic | Added | After original row 18
Aggregator data – ingestion-level test design and execution | Test team (TBC) | RLIS08; confirm ingestion-level expected outputs | Added | After original row 18
Pre-renewals regression testing (separate BI feed) | ? |  | Existing | Original screenshot row 19
Existing BI feed regression testing from CRS | ? |  | Existing | Original screenshot row 20
CRS regression – BICoE test coverage confirmation | Test team / CRS (TBC) | RLIS10; align to rows 19–20; avoid duplicate executions | Added | After original row 20
Quote Cache Deletion design |  |  | Existing | Original screenshot row 21
Quote Cache Deletion IA |  |  | Existing | Original screenshot row 22
Quote Cache Deletion build and test |  |  | Existing | Original screenshot row 23
Quote cache deletion – BICoE test coverage and evidence | Test team (TBC) | RLIS13; coordinate with delivery build/test; ingestion-only coverage | Added | After original row 23
Confused.com quote retention – test design and execution | Test team (TBC) | RLIS12; validate scope and source outputs | Added | After original row 23
Data reconciliations design |  |  | Existing | Original screenshot row 24
Data reconciliations build |  |  | Existing | Original screenshot row 25
Data reconciliations test |  |  | Existing | Original screenshot row 26
Reconciliation – BICoE test design / test data agreement | Test team (TBC) | RLIS11; aligns to existing reconciliation test row | Added | After original row 26
SIT defect triage, retesting and daily status reporting | Test team / Dev / Source teams (TBC) | Record defects, prioritise fixes and provide cycle status | Added | End of tracker
SIT Cycle 2 – conditional regression and retesting | Test team (TBC) | Only if Cycle 1 defects or coverage gaps require it | Added | End of tracker
Personal data access – scope and testing ownership (provisional) | Owner TBC | RLIS14; confirm whether BICoE ingestion validation is needed | Added | End of tracker
Vehicle and area service – scope and testing ownership (provisional) | Owner TBC | RLIS16; Cosmos DB / service scope to be agreed | Added | End of tracker
Non-functional ingestion testing – scope and ownership (provisional) | Owner TBC | RLIS15; NFRs and responsibilities to be agreed | Added | End of tracker
SIT test closure, evidence and sign-off | Test team / PM (TBC) | Complete agreed ingestion test coverage and record open risks | Added | End of tracker

## Tracker Guide
Guide | Details
Source | Recreated from supplied screenshot; original spreadsheet was not provided.
Existing items | 25 original activities retained in their original relative order and wording (visible columns A–C).
Added items | 22 proposed project-level testing activities, shaded light green.
Original owners | Original Resource values copied from screenshot, including blanks and ?.
New owners | Suggested functional owners shown as TBC rather than assigned individuals.
Original dependencies | Original visible Dependency cells were blank; new dependencies are suggestions.
Scope | BICoE ingestion-level coverage only. No Silverish/Silver or DEA-owned validation.
Review | Confirm DLT table inventory and ownership of provisional RLIS14–16, plus CRS regression overlap.