## Sheet1
Activity Planned | Description | Date | Owner | Expected Outcome | Actual Outcome
1. Data Volume Confirmation for Prod and Preprod | Confirm data volume for applying fixes in both environments | 2024-02-22 | Project Team | Team agrees with business on data volume for fixes in both environments | Decision made: Fix applied for two months in preprod, whole data in prod
2. Data Availability | Confirm availability of test data in both environments for testing | 2024-02-22 | Development Team | DEV team confirms availability of test data in both environments | Decision made: Fix applied for two months in preprod, whole data in prod
3. Cloud Cost Estimation and Approval | Check cloud cost estimation, seek Cloud Council approval for preprod and prod release | 2024-02-22 | Project Team | Review with Development and Design teams, obtain Cloud Council approval | -
4. Cloud Cost Estimation and Approval | Check cloud cost estimation, seek Cloud Council approval for preprod and prod release | 2024-02-22 | Project Team | Review with Development and Design teams, obtain Cloud Council approval | -
5. Data Quality Analysis in Preprod | Perform data quality analysis on existing data in preprod | 2024-02-22 | Testing Team | Identify data deviation between preprod and prod | -
6. Obtain Technical Review Approval | Obtain code review approval to push code to preprod | 2024-02-22 | Development Team | Obtain code review approval for preprod deployment | -
7. Establish Connection with PowerBI | Create PowerBI reports using preprod data for comparison | 2024-02-22 | Development Team | Reports point to preprod data for pre vs post comparison | -
8. Capture Databricks and Storage Cloud Cost | Benchmark cloud cost utilization before data load | 2024-02-22 | Test Team | Capture cloud cost utilization before data load | -
9. Perform Initial Data Load with E2P Fix | Load initial data with fix in preprod | 2024-02-22 | Development Team | Successful completion of initial data load in preprod | -
10. Data Validation for Initial Load | Validate initial data load in preprod | 2024-02-22 | Development Team | Successful completion of initial data load testing in preprod | -
11. Data Load and Validation for Incremental Load | Validate incremental data load in preprod | 2024-02-22 | Development Team | Successful completion of incremental data load testing in preprod | -
12. UAT | Conduct User Acceptance Testing in preprod | 2024-02-22 | Business Team | Successful completion of UAT in preprod | -
13. TSR and Cost Analysis - Performance Analysis | Present cloud cost utilization for approval, obtain TSR approval | 2024-02-22 | Project Team | Successful completion of functional and UAT in preprod, obtain signoff on TSR and cloud cost utilization | -
14. Preprod Closure | Pause workflows, ensure proper closure of preprod environment | 2024-02-22 | Development and Test Team | Ensure all workflows are paused, no further activities | -
Activity No. | Activity Planned | Description | Date | Owner | Expected Outcome | Actual Outcome
1 | Data Volume Confirmation for Prod and Preprod Fix | Confirm the data volume required for applying the fix in both pre-production and production environments. | 2024-02-22 | Project Team | The team agrees with the business on the data volume for the fix to be applied in both environments. | The decision has been made to apply the fix for two months in preprod and the entire dataset in production.
2 | Data Availability | Confirm the availability of test data in both environments for testing purposes. | 2024-02-22 | Development Team | The development team confirms the availability of test data in both environments, which was loaded as part of the performance tuning project and will be reused to avoid data load costs in preprod. | Confirmed the data availability based on data loaded as part of the performance tuning project; same data will be reused to avoid data load costs in preprod.
3 | Cloud Cost Estimation and Approval | Check with the development team and design team on the cloud cost estimation shared with them. Send the estimation to the Cloud Council for approval for preprod and prod release. Expecting approval by Friday to plan for preprod release on Monday. | 2024-02-22 | Project Team | Check with the development and design teams on the cloud cost estimation. Obtain approval from the Cloud Council for preprod and prod release. Expecting Cloud Council approval by Friday to plan for preprod release on Monday.
4 | Cloud Cost Estimation and Approval | Check with the development team and design team on the cloud cost estimation shared with them. Send the estimation to the Cloud Council for approval for preprod and prod release. Expecting approval by Friday to plan for preprod release on Monday. | 2024-02-22 | Project Team | Check with the development and design teams on the cloud cost estimation. Obtain approval from the Cloud Council for preprod and prod release. Expecting Cloud Council approval by Friday to plan for preprod release on Monday.
5 | Data Quality Analysis in Preprod for Existing Data | Perform data quality analysis in the preprod layer on existing data at the fact level. | 2024-02-22 | Testing Team | Identify any deviations from the known deviations identified previously as part of the performance tuning project. Analyze to calibrate the deviations in counts, providing the percentage of data deviation expected between prod and preprod.
6 | Obtain Technical Review Approval to Push Code to Preprod | Obtain code review approval to push codes to preprod once Cloud Council approval is obtained. | 2024-02-22 | Development Team | Ensure code review approval is obtained and the code is ready to be pushed to preprod.
7 | Establish Connection with PowerBI from Preprod | Create a report version of the E2P report from preprod data for pre vs. post comparison during UAT. | 2024-02-22 | Development Team | Ensure that reports point to preprod data.
8 | Capture Databricks and Storage Cloud Cost in Preprod | Benchmark the cloud cost utilization by capturing Databricks and storage cloud costs before data load starts. | 2024-02-22 | Test Team | Capture cloud cost utilization before data load and document it.
9 | Perform Initial Data Load for Two Months with E2P Fix | Perform the initial data load in preprod with the fix and notify the test team to perform data validation. | 2024-02-22 | DEV Team | Successfully complete the initial data load in preprod with the fix.
10 | Data Validation for Initial Load | Perform data load validation and notify any observations/issues for the fix. | 2024-02-22 | DEV Team | Successfully complete initial data load testing in preprod and notify the development team for incremental data load and the reporting team for data refresh to allow parallel UAT testing.
11 | Data Load and Validation for Incremental Load Completion | Perform incremental data load validation and notify any observations/issues for the fix. | 2024-02-22 | DEV Team | Successfully complete incremental data load testing in preprod and notify the reporting team for data refresh.
12 | User Acceptance Testing (UAT) | Conduct UAT testing and notify any observations/issues for the fix. | 2024-02-22 | Business Team | Successfully complete UAT in preprod and obtain signoff.
13 | TSR and Cost Analysis- Performance Analysis | Present cloud cost utilization in preprod to the project team for approval to release. Obtain TSR approval. | 2024-02-22 | Project Team | Successfully complete functional UAT in preprod and obtain signoff on TSR and cloud cost utilization.
14 | Preprod Closure | Ensure all workflows are paused and no other activities are performed to properly close the environment. | 2024-02-22 | Development & Test Team | Ensure all workflows are paused and no activities are performed.