## Slide 1
UAT Objective (Business Perspective)
The primary objective of this UAT is for business users to validate and accept that the data and pricing outputs generated from both the online and offline Radar environments are aligned. This alignment ensures that the model behaves consistently across both platforms, enabling faster and more confident validation before deploying the model into actual live production.
Through this process, business aims to:
Confirm pricing logic is functioning as intended across systems.
Reduce validation cycles by ensuring the offline environment reflects live behavior.
Build confidence in the model’s accuracy prior to production rollout.

## Slide 2
Phase | Activity | Owner | Tentative Timeline
Preparation | UAT planning, data setup, environment readiness | QA + Business | Week 1 (pre-UAT)
SIT Monitoring | Track SIT progress to 80% completion | QA | Ongoing during SIT
UAT Kickoff | UAT readiness confirmation and walkthrough | QA + Business | Day 0
UAT Execution | Test case execution, reconciliation checks | Business Users | Day 1–10 (2 weeks max)
Triage & Fixes | Daily defect triage, dev fix & retesting | QA + Dev + Biz | Parallel with execution
UAT Closure | Final validations, sign-off | Business Owner | Day 11–14 or earlier
Indicative Timeline
Note: If high-priority defects are encountered, timelines may be adjusted with joint agreement.

## Slide 3
Support Expected from Testing Team
To enable efficient and accurate validation by business users, the following support is expected from the QA/testing team during the UAT phase:
1. Test Data & Scenario Preparation
Provide pre-aligned datasets for both online and offline environments to ensure business can compare outputs effectively.
Share sample test cases and help prepare additional test scenarios based on business inputs.
Highlight known limitations or configurations in the test environment.
2. Reconciliation Support
Assist in generating comparison reports or logs between online and offline pricing outputs.
Provide guidance on interpreting discrepancies, especially in case of expected deviations (e.g., rounding, fallback behavior).
Help business users identify if issues are related to data, configuration, or logic.
3. Environment & Access Setup
Ensure both online and offline environments are:
  Stable
  Data-synced
  Accessible to UAT participants with proper credentials
4. Issue Logging & Resolution Support
Provide UAT issue tracker (e.g., Excel sheet, JIRA board) with clear logging templates.
A testing POC should be available to help business:
  Log issues correctly
  Categorize severity
  Attach necessary evidence (e.g., screenshots, logs)
5. Daily Sync & Triage Participation
Attend daily stand-ups or checkpoints to:
  Review progress
  Discuss blockers
  Prioritize defect fixes
6. Knowledge Support
Be available for on-the-spot clarifications regarding test coverage, flow behavior, or system configurations.
Share any known SIT defects or warnings that may impact UAT.

## Slide 4
UAT Closure Criteria
UAT will be considered complete and ready for closure when the following conditions are met. A formal sign-off will be provided by the business team, with conditional options if necessary.
✅ Full Sign-Off Criteria
100% of planned UAT test scenarios are executed.
All critical and high-priority defects are closed or resolved.
Reconciliation results between online and offline pricing outputs are within acceptable deviation limits (e.g., < ±0.1% or as agreed).
No open blockers for go-live decision.
Business confirms functional acceptance of the solution.
⚠️ Conditional Sign-Off Criteria
In certain cases, business may grant a conditional sign-off under the following conditions:
A small number of low/medium priority defects remain open, but they:
  Do not impact critical pricing logic
  Have agreed workaround or fix plan before go-live
Minor reconciliation mismatches are:
  Understood and accepted as environment-specific
  Not material to the pricing outcome
In such cases, business must document the rationale and list deferred issues for post-UAT resolution or go-live readiness.