## Detailed Task List
Phase | Task | Owner | Start Date | End Date | Remarks | Duration (Days)
Pre-Phase (Entry Readiness) | Confirm POCs for all workstreams | E2E Test Manager | 2025-11-10 | 2025-11-12 | Before E2E readiness | 2
Pre-Phase (Entry Readiness) | Share finalized E2E test calendar and environment plan | E2E PMO | 2025-11-10 | 2025-11-13 | Program alignment | 3
Pre-Phase (Entry Readiness) | Validate all upstream SIT testing complete, no open S1/S2 defects | Athena / MQS / RADAR | 2025-11-12 | 2025-11-15 | Entry gating item | 3
Pre-Phase (Entry Readiness) | Finalize E2E scenarios (NB, MTA, Renewal, Requote) and scope | Athena (Vijay) / E2E Lead | 2025-11-11 | 2025-11-17 | Scenario baseline | 6
Pre-Phase (Entry Readiness) | Confirm schema and message contracts (MQS to BICOE) | MQS (Adrian) / BICOE | 2025-11-15 | 2025-11-18 | Data contract baseline | 3
Pre-Phase (Entry Readiness) | Deploy ingestion, transformation, ADF pipelines in PyGo | BICOE DevOps | 2025-11-20 | 2025-11-25 | Stable environment needed | 5
Pre-Phase (Entry Readiness) | Perform connectivity checks (Event Hub, ADLS, Cosmos, EDM) | BICOE Data Ops | 2025-11-24 | 2025-11-28 | Before data flow testing | 4
Pre-Phase (Entry Readiness) | Validate orchestration dry run and incremental loads | BICOE Test Lead | 2025-11-25 | 2025-11-30 | Dry-run evidence | 5
Pre-Phase (Entry Readiness) | Confirm UAT access and security for Pricing & Underwriting | Pricing / E2E Env Team | 2025-11-25 | 2025-11-30 | Before Cycle 1 | 5
Pre-Phase (Entry Readiness) | Entry Readiness review and Go/No-Go | E2E Test Manager | 2025-12-01 | 2025-12-02 | Authorize Cycle 1 start | 1
Cycle 1 – Dec (Risk-Based) | Execute E2E transactions via Athena | Athena (Vijay) | 2025-12-03 | 2025-12-06 | Generates MQS + Interaction messages | 3
Cycle 1 – Dec (Risk-Based) | Validate message routing from Mule to MQS | Mule (Ashutosh) / MQS (Adrian) | 2025-12-03 | 2025-12-07 | Parallel run | 4
Cycle 1 – Dec (Risk-Based) | Verify Event Hub data for BICOE ingestion | MQS (Adrian) | 2025-12-05 | 2025-12-08 | Pre-ingestion validation | 3
Cycle 1 – Dec (Risk-Based) | Run BICOE ingestion (Bronze layer) | BICOE MI Team | 2025-12-08 | 2025-12-10 | Dependent on MQS messages | 2
Cycle 1 – Dec (Risk-Based) | Validate Bronze structure (6 MQS message types) | BICOE Test Lead | 2025-12-09 | 2025-12-11 | Schema and counts | 2
Cycle 1 – Dec (Risk-Based) | Validate Silverish enrichment decompression | BICOE Test Analyst | 2025-12-10 | 2025-12-12 | Bronze done | 2
Cycle 1 – Dec (Risk-Based) | Validate Silver layer transformation joins | BICOE Test Analyst | 2025-12-12 | 2025-12-14 | Silverish done | 2
Cycle 1 – Dec (Risk-Based) | Validate Gold layer EDM mappings | BICOE Data Engineer | 2025-12-14 | 2025-12-16 | Silver complete | 2
Cycle 1 – Dec (Risk-Based) | Run data quality checks (duplicates, nulls, etc.) | BICOE Test Team | 2025-12-15 | 2025-12-17 | Post-transform | 2
Cycle 1 – Dec (Risk-Based) | Share offline data for reconciliation | BICOE Test Lead | 2025-12-17 | 2025-12-18 | With RADAR + MQS | 1
Cycle 1 – Dec (Risk-Based) | Validate online vs offline reconciliation | RADAR (Paul) / MQS (Adrian) / BICOE Support | 2025-12-18 | 2025-12-20 | Compare datasets | 2
Cycle 1 – Dec (Risk-Based) | Consolidate defects & triage daily | E2E Test Manager | 2025-12-08 | 2025-12-22 | Ongoing | 14
Cycle 1 – Dec (Risk-Based) | Cycle 1 sign-off | BICOE Test Manager / E2E Lead | 2025-12-21 | 2025-12-23 | Entry to Cycle 2 | 2
Cycle 2 – Jan (MVP) | E2E test data refresh and model deployment | Athena / MQS | 2026-01-02 | 2026-01-05 | Post-holiday data | 3
Cycle 2 – Jan (MVP) | Re-validate MQS schema post-deployment | MQS (Adrian) | 2026-01-04 | 2026-01-06 | Schema consistency | 2
Cycle 2 – Jan (MVP) | Run BICOE ingestion (Bronze) new dataset | BICOE MI Team | 2026-01-06 | 2026-01-10 | Ready for next layers | 4
Cycle 2 – Jan (MVP) | Validate Silverish/Silver mappings and joins | BICOE Test Team | 2026-01-10 | 2026-01-14 | Bronze complete | 4
Cycle 2 – Jan (MVP) | Validate Gold layer – EDM Core Risk | BICOE Data Engineer | 2026-01-14 | 2026-01-17 | Silver complete | 3
Cycle 2 – Jan (MVP) | Validate Radar Feature Set mapping | BICOE / RADAR | 2026-01-17 | 2026-01-20 | Dependent on EDM | 3
Cycle 2 – Jan (MVP) | Validate Pricing View dataset (Continuity of Service) | BICOE / Pricing | 2026-01-20 | 2026-01-22 | Radar features ready | 2
Cycle 2 – Jan (MVP) | Publish datasets for UAT | BICOE Test Manager / E2E Lead | 2026-01-22 | 2026-01-24 | Ready for UAT | 2
Cycle 2 – Jan (MVP) | Cycle 2 exit review | BICOE / E2E Lead | 2026-01-24 | 2026-01-25 | Entry to Pre-Prod | 1
Pre-Prod Dry Run & UAT Support | Dry run of ingestion/orchestration | BICOE Data Ops | 2026-01-26 | 2026-01-28 | Environment parity | 2
Pre-Prod Dry Run & UAT Support | Validate orchestration schedules & alerting | BICOE Data Ops | 2026-01-26 | 2026-01-29 | Runbook verified | 3
Pre-Prod Dry Run & UAT Support | Provide dataset access for UAT | BICOE / Env Team | 2026-01-24 | 2026-01-31 | Aligns with UAT start | 7
Pre-Prod Dry Run & UAT Support | Assist with UAT data extraction | BICOE Support Team | 2026-01-24 | 2026-01-31 | UAT support | 7
Pre-Prod Dry Run & UAT Support | Monitor ingestion/orchestration issues | BICOE Data Ops | 2026-01-24 | 2026-01-31 | Real-time UAT support | 7
Pre-Prod Dry Run & UAT Support | Collect UAT feedback and defects | E2E Test Manager / BICOE | 2026-01-27 | 2026-02-02 | Continuous triage | 6
Pre-Prod Dry Run & UAT Support | Final UAT sign-off and dry-run summary | E2E Test Manager / BICOE | 2026-02-02 | 2026-02-05 | Project closure | 3