## Sheet1
Title | Description
Refresher – Review Existing Test Strategy & Plan | Revisit previously created test strategy, test plan, and PoC automation. Validate assumptions against current CDA architecture (Clone, SCD, ODS Views). Identify gaps due to changes in ingestion (S3/CDA vs ADF/RR). Update scope for parallel run validation.
Refresher – Review Existing Automation Framework | Analyze current Databricks scripts for RR vs CDA comparison. Identify reusable components (row hash, schema compare, count checks). Refactor for scalability to ~2k tables and new CDA layers (Clone/SCD/ODS).
Environment Validation – Databricks & Catalog Setup | Verify access to both catalogs (RR/ADF and CDA/S3). Confirm table availability across Bronze (Clone/SCD) and ODS Views. Validate permissions, clusters, and runtime versions. Ensure checkpoint/watermark tables are accessible.
Environment Validation – Data Availability Check | Confirm data availability for selected snapshot date (RR side) and watermark (T_ASOF) on CDA side. Validate completeness of ingestion jobs (no missing partitions/files).
Define Scope – Table Mapping (RR vs CDA) | Create mapping between RR ODS tables/views and CDA equivalents (Clone/SCD/ODS). Document key columns, partition columns, and expected row counts. Maintain mapping in a config table for automation.
Identify Tables with Large Columns (~1 MB) | Scan schema metadata to identify columns with large data types (e.g., CLOB, TEXT, VARBINARY, JSON). Flag tables where column size may approach ~1 MB. These require special validation for ingestion, storage, and comparison performance.
Validate Large Column Handling (1 MB Data) | Create targeted tests for identified tables: ensure data is fully ingested (no truncation), preserved in format (string/binary), and matches between RR and CDA. Validate row-hash logic supports large payloads without failure.
Schema/DDL Comparison Automation | Implement automated comparison of schema between RR and CDA tables: column names, types, nullability, partitioning. Normalize types (e.g., varchar vs string). Flag mismatches and store results.
Data Format Validation (Parquet/Delta) | Validate CDA data is correctly stored in Parquet/Delta format. Check compression, partitioning, schema evolution handling. Ensure compatibility with downstream ODS Views.
Watermark (T_ASOF) Validation | Identify ingestion watermark from CDA tables (max cdc_commit_ts). Define global T_ASOF as minimum across tables. Validate correctness to ensure “point-in-time” comparison.
Snapshot Alignment Validation (RR vs CDA) | Align RR snapshot date (S) with CDA watermark (T_ASOF). Ensure both datasets represent the same point in time before comparison.
Clone Table Validation (Raw CDC) | Validate Clone tables contain all CDC events (I/U/D). Check for duplicates, missing records, and correct ingestion ordering.
SCD Table Validation (CDC Processed) | Validate SCD logic: correct start_at, end_at, is_current. Ensure one current record per key and no overlapping intervals.
ODS View Validation (Core Comparison Layer) | Validate CDA ODS Views replicate RR ODS functionality. Compare row counts, keys, and full-row hash outputs. Ensure downstream compatibility with Silver/Gold.
Row-Level Comparison (Keyed Tables) | Implement row-to-row comparison using keys + full-row hash. Identify missing, extra, or mismatched rows. Store discrepancies.
Row-Level Comparison (No Key Tables) | Implement multiset (bag) comparison using full-row hash. Compare counts of identical rows between RR and CDA.
Partition-Level Validation | Validate partition counts (e.g., by snapshot_date or business partition). Ensure no missing partitions or skew between RR and CDA.
Automation Framework Enhancement (Scalability) | Extend automation to handle ~2k tables using config-driven approach. Add batching and parallel execution via Databricks Workflows.
Automation Execution – PoC Validation | Run PoC on subset of critical tables. Validate accuracy of comparison logic. Fine-tune performance and thresholds.
Automation Execution – Full Run (RR vs CDA) | Execute automation across all mapped tables. Capture results in recon table. Identify discrepancies and categorize issues.
Defect Logging & Resolution Workflow | Define process to log mismatches as Jira defects. Categorize by schema, data, CDC, or timing issues. Track resolution and retesting.
Manual Testing – Critical Tables | Perform manual validation on high-risk tables (financial, policy, claims). Cross-check with business logic and sample queries.
Manual Testing – Large Data Columns | Manually inspect large column data (≥1 MB) for truncation, encoding issues, or mismatches. Validate UI/API consumption if applicable.
Regression Testing (RR vs CDA) | Re-run comparison after fixes or schema changes. Ensure no regressions introduced in CDA pipeline.
Performance Testing – Databricks Connector & Queries | Validate performance of CDA ingestion and comparison queries. Measure runtime, resource usage, and scalability under load.
Scheduling & Orchestration Setup | Configure Databricks Workflows to run comparison jobs daily (and optionally hourly). Ensure dependency on ingestion completion.
Monitoring & Alerting Setup | Set up alerts for failed comparisons (email/Slack). Build dashboard for PASS/FAIL status across tables.
Data Quality KPI Dashboard | Create dashboard showing counts, mismatches, schema issues, and trends over time. Use for decision-making during parallel run.
Parallel Run Monitoring (RR vs CDA) | Monitor both pipelines in production for a defined period. Track anomalies, trends, and stability.
Cutover Readiness Assessment | Define criteria for switching (e.g., 7 consecutive PASS runs). Validate all critical tables meet thresholds.
Switch-Over Testing (ODS Views) | Test renaming/switching ODS views from RR to CDA. Validate Silver/Gold pipelines continue without issues.
Post-Switch Validation | After cutover, validate data consistency for a defined period. Monitor for late issues or discrepancies.
Final Sign-Off (TSR/QA Approval) | Document results, defects, and resolutions. Obtain formal sign-off for CDA migration.